## Project Summary
Sl. No | Project Name | Deal Value | Growth/Core | Project Type | Delivery Region | SOW Type | Contract Type | Status | Resources FTE | Resources CW | RAG Status | Issues | Issues / Risks Captured | Comments | SOW Signed on | Contract [SFDC] End date | Sales / GTM | Team Member | Expected Release Date | Availability
1 | Hub International-Fixed Price-Prepaid-PR-005338 | 1021714 | Growth | Gen AI/DU/IDP | India | MS | Fixed Fee | In Progress | 1.25 | 18.25 | Green | No |  |  | 2023-03-31 | 2026-04-30
2 | BJ's Wholesale Club-Hybrid-100% discounted-Service Credit Prepaid-PR-005394 | 175000 | Growth | Comms Mining | India/US | Delivery | Service Credit | In Progress | 2.5 | 2 | Green | No |  |  | 2023-01-27 | 2026-04-26
3 | DENSO International Ameri-Time and Materials-Prepaid-006333 | 15000 | Growth | Gen AI/DU/IDP | India | MS | T&M | In Progress | 0.5 | 0 | Green | No |  |  | 2023-07-12 | 2025-07-13
4 | Group 1 Automotive-Time and Materials-POD-008966 | 123750 | Growth | Gen AI/DU/IDP | India | Staff Aug | T&M | In Progress | 0 | 2 | Green | No | Contracted efforts would be consumed by 15 June 2025 Informed AE - Lindsay Kincy on 02 May 2025 | Decision awaited - whether customer will renew contract or release resources | 2024-07-11 | 2026-07-10 |  | Raja Christopher Ponvijay Nirmal | 2025-06-15
5 | Lydonia Te-America Fujiku-Time and Materials-POD-009156 | 93934.77 | Growth | Gen AI/DU/IDP | India | Staff Aug | T&M | In Progress | 0 | 1 | Green | No |  |  | 2024-08-30 | 2026-09-02
6 | Lydonia Te-USI Service Co-Time and Materials-POD-008284 | 41184 | Growth | Gen AI/DU/IDP | India | Staff Aug | T&M | In Progress | 0.25 | 0 | Green | No |  |  | 2023-12-01 | 2025-11-30
7 | PACCAR Inc.-Fixed Price-Prepaid-009306 | 162000 | Growth | Gen AI/DU/IDP | India | MS | Fixed Fee | In Progress | 0.25 | 3.5 | Green | No |  |  | 2024-10-22 | 2026-10-21
8 | Tenet Health-Fixed Price-Partial-Prepaid-007914 | 225170 | Growth | Gen AI/DU/IDP | India/US | Delivery | Fixed Fee | On Hold | 1 | 1 | Green | No |  |  | 2023-09-20 | 2025-09-24
9 | Workday Inc.-Fixed Price-Prepaid 100% Discounted-009613 | 65780 | Growth | Gen AI/DU/IDP | India/US | Delivery | Fixed Fee | In Progress | Green | No | Green | No |  |  | 2025-01-23 | 2026-03-22
10 | Deloitte Global Services-Hybrid-Service Credit Prepaid-PR-008208 | 1470000 | Growth | Gen AI/DU/IDP | India | Delivery | Service Credit | In Progress | 0.5 | 2.75 | Green | No |  |  | 2023-10-30 | 2026-10-30
11 | Intel Corporation-Time and Materials-POD-009522 | 240000 | Growth | Gen AI/DU/IDP | India | Staff Aug | T&M | In Progress |  |  | Green | No |  |  | 2024-12-16 | 2026-12-15
12 | Kaiser Foundation Hosp-Fixed Price-Service Credit Prepaid-100% Discounted-008112 | 2300000 | Growth | Process Mining | India/US | Staff Aug | Service Credit | In Progress | 1 | 0 | Green | No |  |  | 2023-10-13 | 2025-10-15
13 | Bank of America (Global)-Time and Materials-Prepaid-009525 | 52800 | Core | Core RPA | India | Staff Aug | T&M | In Progress |  |  | Green | No |  |  | 2024-12-06 | 2025-06-30
14 | Bank of New York Mellon-Hybrid-SC Prepaid-100% discounted-3 year-PR-004868 | 1600000 | Core | Core RPA | India/US | MS | Service Credit | In Progress | 2.5 | 1 | Green | No |  |  | 2023-03-31 | 2026-03-30
15 | Intuit Inc.-Time and Materials-Prepaid-PR-008662 | 78100 | Core | Core RPA | India | Staff Aug | T&M | In Progress | 0 | 1 | Green | No | Dev efforts exhausted - Chaitalee Shilke 29 April - New SOW Signature in Progress Start at Risk approved by Samuel Mongeau 27 May - Awaiting Project creation | Extension for 1 year in Progress - Awaiting SOW customer Signature | 2024-03-18 | 2026-03-17 | Tylor Basas / Spencer Miller | Chaitalee Shilke
16 | Intuit Inc.-Time and Materials-Prepaid-100% Discounted-009564 | 325080 | Core | Core RPA | India/US | Staff Aug | T&M | In Progress |  |  | Green | No | Santosh & Sidappa |  | 2025-01-03 | 2025-07-31
17 | Leica Microsystems Inc.-Time and Materials-Prepaid-008832 | 105600 | Core | Core RPA | India | MS | T&M | In Progress | 0 | 1.25 | Green | No |  |  | 2024-05-09 | 2026-05-20
18 | Lydonia Te-Angelo Gordon-T&M-POD-008729 | 107575.76 | Core | Core RPA | India | Staff Aug | T&M | In Progress | 0.25 | 1.5 | Green | No |  |  | 2024-04-30 | 2026-04-29
19 | Take-Two Interactive Soft-Hybrid-Prepaid-008816 | 78100 | Core | Core RPA | India | Staff Aug | T&M | In Progress | 0 | 1 | Green | No |  | Sandeep B | 2024-04-30 | 2026-04-29
20 | Take-Two Interactive Soft-Time and Materials-Prepaid-008666 | 91300 | Core | Core RPA | India | Staff Aug | T&M | In Progress | 0 | 1 | Green | No |  | Syed Muzzammil | 2024-03-18 | 2026-03-19
21 | Take-Two Interactive Soft-Time and Materials-Prepaid-009051 | 78100 | Core | Core RPA | India | Staff Aug | T&M | In Progress | 0 | 1 | Green | No |  | Sridhar Amudala | 2024-07-24 | 2026-07-23
22 | Veolia WTS Services USA-Fixed Price-POD-008558 | 81000 | Core | Core RPA | India | MS | Fixed Fee | In Progress | 0.25 | 1 | Green | No |  |  | 2024-01-19 | 2026-10-23
23 | Carahsoft-New York Power-Fixed-POD-005090 | 108325 | Core | Core RPA | India/US | Delivery | Fixed Fee | In Progress | 1.5 | 0 | Green | No |  | Deeksha SA continues | 2023-05-26 | 2025-05-30
24 | Vialto Partners-Hybrid-Service Credit Prepaid-100% Discounted-006378 | 115500 | Core | Core RPA | India/US | Staff Aug | Service Credit | In Progress | 1 | 0 | Green | No |  | George, Ranjith | 2023-07-20 | 2025-07-19
25 | Citizens Bank National A-Fixed Price-100% disc.-Service Credit Prepaid-008086 | 1300000 | Competitive Migration | BP to UiPath | India | Staff Aug | Fixed Fee | In Progress | 1.5 | 6 | Green | No |  |  | 2023-11-23 | 2026-11-23
26 | Fresenius Medical Care Ho-Hybrid-Service Credit Prepaid-100% discounted-007929 | 319550 | Competitive Migration | BP to UiPath | India/US | Delivery | Service Credit | In Progress | 0.25 | 4.25 | Green | No |  |  | 2023-08-30 | 2025-08-30
27 | Wells Fargo (Global)-Hybrid-Service Credit-100% Disc- Prepaid-009742 | 1600000 | Competitive Migration | BP to UiPath | India | Delivery | Service Credit | In Progress |  |  | Green | No |  |  | 2025-04-01 | 2026-09-30
28 | JP Morgan Chase(Global-Fixed Price-Service Credit Prepaid-100% Discounted-008300 | 35345 | Platform Migration | Infra & Platform Migration | India/US | Delivery | Service Credit | In Progress | 0.25 | 2 | Green | No |  |  | 2023-11-28 | 2026-11-27
29 | BetterUp Inc-Hybrid-Service Credit Prepaid-004953 | 136000 | Growth | Gen AI/DU/IDP | India | MS | Fixed Fee | In Progress | 0 | 1.25 | Green | No |  |  | 2022-10-31 | 2025-07-31
30 | MemorialCare Health Syste-Fixed Price-Prepaid-PR-006221 | 76000 | Growth | Gen AI/DU/IDP | India | MS | Fixed Fee | In Progress | 0.25 | 1.5 | Green | No |  |  | 2023-07-01 | 2026-07-01
31 | EY US-Adobe Systems-Time and Materials-Prepaid-100% Discounted-009350 | 4800 | Growth | Gen AI/DU/IDP | India | Staff Aug | T&M | In Progress |  |  | Green | No |  |  | 2024-10-26 | 2025-11-11
32 | PT Indosat Tbk-Fixed Price-POD-008937 | 2500000 | Growth | Test Automation | India | Delivery | Fixed Fee | In Progress |  |  | Green | No |  |  | 2024-06-20 | 2026-06-27
33 | Organik Kimya San. Tic. A-Fixed Price-Partial Prepaid-009058 | 54199 | Growth | Process Mining | India | Delivery | Fixed Fee | In Progress |  |  | Green | No |  |  | 2024-07-30 | 2026-07-29
34 | Massachusetts Mutual Life-100%discounted-Service Credit Prepaid-008575 | 150000 | Growth | Gen AI/DU/IDP | India/US | Staff Aug | Service Credit | In Progress |  |  | Green | No |  |  | 2023-10-31 | 2025-10-30
35 | Hub International-Time and Materials-POD-009736 | 115200 | Growth | Comms Mining | India | Staff Aug | T&M | In Progress | Green | No | Green | No |  |  | 2025-01-31 | 2027-01-30
36 | Hub International-Time and Materials-POD-009743 | 76800 | Growth | Comms Mining | India | Staff Aug | T&M | In Progress |  |  | Green | No |  |  | 2025-01-31 | 2027-01-30
37 | Deloitte AUS AA Migration | 170855 | Competitive Migration | AA to UiPath | India | Delivery | Service Credit | In Progress |  |  | Green | No |  |  | 2023-10-30 | 2026-10-30
38 | Deloitte Smart Finance | 39840 | Growth | Gen AI/DU/IDP | India | Delivery | Service Credit | In Progress |  |  | Green | No |  |  | 2023-10-30 | 2026-10-30
39 | MGM Resorts International-Fixed Price-Prepaid-009499 | 99641 | Growth | Gen AI/DU/IDP | India/US | Delivery | Fixed Fee | In Progress |  |  | Green | No |  |  | 2024-12-20 | 2026-12-19
40 | CAMC Health System-Hybrid-POD | 328367 | Growth | Gen AI/DU/IDP | India/US | Staff Aug | Fixed Fee | In Progress |  |  | Green | No |  |  | 2025-01-28 | 2027-01-29
41 | The Promptcare Companies-Fixed Price-100% DISC-Prepaid-009890 | 273810 | Growth | Gen AI/DU/IDP | India | Delivery | Fixed Fee | In Progress |  |  | Green | No | All India Staffing - DU |  | 2025-03-18 | 2026-03-18
42 | The Promptcare Companies-Fixed Price-Prepaid-009891 | 278029 | Growth | Gen AI/DU/IDP | India | Delivery | Fixed Fee | In Progress |  |  | Green | No | All India Staffing - DU |  | 2025-03-18 | 2027-03-18
43 | Homeserve USA-Fixed Price-Prepaid-009745 | 537150 | Growth | Gen AI/DU/IDP | India/US | Delivery | Fixed Fee | In Progress |  |  | Green | No |  |  | 2025-01-30 | 2027-01-30
44 | Houston Methodist Hospita-Hybrid-Prepaid-100% Discounted-009695 | 100000 | Growth | Gen AI/DU/IDP | India/US | Delivery | Service Credit | In Progress | Green | No | Green | No |  |  | 2025-01-28 | 2026-01-27
45 | Comcast (Cable Communicat-Fixed Price-Prepaid-009360 | 82540 | Growth | Gen AI/DU/IDP | India/US | Delivery | Fixed Fee | In Progress |  |  | Green | No |  |  | 2024-10-31 | 2026-10-30
46 | Alliant Credit Union-Time and Materials-POD-009664 | 196432 | Growth | Gen AI/DU/IDP | India/US | Delivery | T&M | In Progress |  |  | Green | No |  |  | 2025-01-24 | 2027-01-23
47 | Wabtec Corporation-Hybrid-Prepaid-100% Discounted-009666 | 46040 | Core | Core RPA | India/US | Delivery | T&M | On Hold |  |  | Green | No |  |  | 2025-02-11 | 2025-05-19
48 | PepsiCo Inc-Hybrid-Service Credit-100% DISC-Prepaid-009972 | 200000 | Platform Migration | Infra & Platform Migration | India | Staff Aug | Service Credit | In Progress |  |  | Green | No |  |  | 2025-04-08 | 2026-04-08
49 | Lydonia Te-Snap-On Credit-Time and Materials-POD_ PR-009958 | 124406 | Core | Core RPA | India | Staff Aug | T&M | In Progress |  |  | Green | No |  |  | 2025-04-02 | 2027-04-01
50 | Lydonia Te-Angelo Gordon-Time and Materials-POD-009816 | 107575 | Core | Core RPA | India | Staff Aug | T&M | In Progress |  |  | Green | No |  |  | 2025-02-13 | 2027-02-12
51 | Google Inc.-Fixed Price-Prepaid-100% Discounted-009073 | 5402500 | Growth | Test Automation | India/US | Staff Aug | Service Credit | Yet to Start |  |  | Green | No |  |  | 2024-07-31 | 2027-09-30
52 | Nissan North America-Time and Materials-Prepaid-PR-007895 | 12000 | Core | Core RPA | India | Staff Aug | T&M | Yet to Start |  |  | Green | No |  |  |  | 2025-08-07
53 | PRESIDENT INFORMATION COR-T&M-Prepaid-100% Discounted-009383 |  | Growth | Test Automation | India | Delivery | Service Credit | Yet to Start |  |  | Green | No |  |  |  | 2025-11-06
54 | PLDT - https://uipath.lightning.force.com/lightning/r/Account/0011Q000026mb6zQAA/view |  | Growth | Test Automation | India | Delivery | Fixed Fee | In Progress |  |  | Green | No
55 | Deloitte |  | Growth | Test Automation | India/US | Delivery | Fixed Fee | Yet to Start |  |  | Green | No
56 | Prudential |  | Growth | Process Mining | India | Delivery | Fixed Fee | Yet to Start |  |  | Green | No
57 | Amazon - TSI Automation (PS) |  | Growth | Gen AI/DU/IDP | India/US | Delivery | Fixed Fee | Yet to Start |  |  | Green | No
58 | Tokyo Electron U.S. Holdi-Fixed Price-Prepaid-008051 | 199500 | Growth | Gen AI/DU/IDP | India/US | Delivery | Fixed Fee | In Progress |  |  | Green | No |  |  | 2024-03-26 | 2026-03-28
59 | Amazon - Global Freight P-Fixed Price-Prepaid-009950 | 74994 | Core | Core RPA | India/US | Delivery | Fixed Fee | Yet to Start |  |  | Green | No |  |  | 2025-04-01 | 2027-03-31
60 | Icertis Inc.-Fixed Price-Service Credit Prepaid | 1000000 | Growth | Gen AI/DU/IDP | India | Delivery | Service Credit | Yet to Start |  |  | Green | No |  |  | 2025-01-31 | 2027-01-30
61 | Onity Group Inc-Fixed Price-Prepaid-010078 | 51920 | Growth | Gen AI/DU/IDP | India | Delivery | Fixed Fee | In Progress |  |  | Green | No |  |  | 2025-05-05 | 2027-04-05
62 | FinThrive Revenue Systems-Hybrid-Service Credit Prepaid-100% Discounte-PR-009904 | 500000 | Growth | Gen AI/DU/IDP | India/US | Delivery | Service Credit | Yet to Start |  |  | Green | No
63 | Apple-Fixed Price-Service Credit Prepaid 100% Discounted-PR-010148 | 2300000 | Growth | Gen AI/DU/IDP | India/US | Delivery | Service Credit | Yet to Start |  |  | Green | No
Note on C10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Zero $ SOW- extension of PR-008494

## Memorial Sloan Kettering Cancer
Name | Process | Phase | ETA | Efforts Available | Remarks | Concerns | Mitigation
Karthik Deshpande | PAS002_Docuent Classification and Splitting | Development |  |  | 02/25- Development completed per the tasks assigned on DU & IXP
Sachdeep Singh

## Columbus State University
Name | Process | Phase | ETA | Efforts Available | Remarks | Concerns | Mitigation
Sarita Shukla | Invoice Processing (Voucher Creation) | Design |  |  | 12/11 - DU training in progress, additional test data requested from Biz
12/18 - all access enabled except only , that is awaited by 12/19. DU model training in progress, test data received this week
Sachdeep Singh

## Endurance
Name | Process | Phase | ETA | Efforts Available | Remarks | Concerns | Mitigation
Hitesh Kumar | Sompo Remittance Advice | Development |  | 360 | 12/08 - DU development nearig copletion, model training being worked out 12/29 - completed the development and and provided a Demo .awaiting customer feedback | 12/29 - As of now they do not have a VM setup or an UAT license for bot to be deployed, they are in contact with sales team | 12/29 - Assuming Sales to provide temporary license

## JCI
Name | Process | Phase | ETA | Efforts Available | Remarks | Concerns | Mitigation
Shivanagouda Naik | United rentals | Discovery |  |  | 12/01 - Discovery in progress, Dev start delayed due to US holidays
12/08 - of the 5 Application access, only 1 isyet to be enabled, POC planned to satrt from today
12/15 - Still discovery in progress, PDD review today, PDD approval expected by 12/17
12/15- 3 applicatons access yet to be enabled

## Voya
Name | Process | Phase | ETA | Efforts Available | Remarks | Concerns | Mitigation
Dharunya / Mina | Stop loss development - POC | POC |  |  | 11/21 - POC completed
Dharunya / Mina | Stop loss development - Phase II | Dev | TBD |  | 12/16 - 2 brokers demo given to customer and received positive feedback, 3rd broker dev in progress, remaining 6 brokers requirement yet to be received 01/13 - 3 brokers dev completed, UAT planned on 01/21, deayed due to test cases 01/13 - Its Planned to take 4 weeks per broker 02/10- Potential changes expected, decission in incorporating them is awaited from PM 02/17 -Dev in progress for the USI Broker 02/24 - UAT planned to start by 02/26 03/03 - UAT in progress, code review completed by Voya dev team 03/03 - Dev in progress for 3 additional brokers [ USI, Cottingham Butler, HUB] | 02/24 - UiPath suggested to do with 2 brokers, however customer has availabile info only on 1 Broker
Anshuman | Comms Mining Matrix reporting | Prod | 2025-11-16 |  | 11/16 - Deployed in Prod
Anshuman | Insigts reporting automation | Prod |  |  | 12/16 - UAT in progtess, API based enhancements being incorporated 01/13 - Deployed in prod 02/06 - Handed over to Voya IT Support
Anshuman | EB Sales Comms Mining Use Case - Stream 1 | Prod |  | 32 | 12/16 - requirement for 5 level completed, ETA 01/22/2026 01/13 - dev planned to complete by -1/16 02/10 - Deployed in Prod, hyper care signed off, however biz changes are being developed 02/17 - Changes being incorporated, planed prod deployment nex week - 02/23 03/03 - Live in Prod, biz approved hyper care, 1 specific scenario alone to be tested, that couldn't be covered due to very low volume
Anshuman | Accidet Claim - Agentic |  |  |  | 03/03 - UI automation developed by US developer is now being converted to API, integrated with Mastero, 50% of code is now changed per new architecture.

## Liberty
Name | Process | Phase | ETA | Efforts Available | Remarks | Concerns | Mitigation
Usama Mirakar | Frontsheet Generation | Dev | 2025-12-18 | 185 | 02/25 - Frontsheet word doc generation for all layers is completed, testing planned wth PO today, cosmetic changes likely to go on for next few weeks basis PO feedback. Dev and Deployment in progress, on 03/18 - pre prod testing planned,

## Apple
Name | Process | Phase | ETA | Efforts Available | Remarks | Concerns | Mitigation
Nihith Shubham | Charter Forwarder | Production |  | 68 | Development in Progress 09 July - Access was rewoked 07 & 08, enabled on 09 July 16 July - Deployed in Prod, biz demo tomorrow 13 Aug - Hyper care Sign off awaited 20 Aug - Handed over to Apple Support Team 03 Sep - Proposed to move from AWS to SIM cloud - server access awaited 24 Sep - Server access still not enabled, expecting resolution by weekending 26/09 | 17 Sep - server access awaited | Vanisri to enable system account access
Nihith Shubham | 90x Block | Development | 2025-10-07 |  | 13 Aug - SDD in Progress 20 Aug - Development in Progress 03 Sep - Dev in progress, 17 Sep - All blockers resolved and dev in prgress 24 Sep - development in progress
SAM | Re-uasble component for Slack | Production |  |  | 09 July - development in Progress 16 July - troubleshooting in progress on Integration services approach on security features. 13 Aug - Published in Prod
SAM | Vader Street Glide | Hyper Care | 2025-08-20 |  | 13 Aug - Hyper care in Progress 03 Sep - KT Completed, awaiting confirmation, 17 Sep - documentation in progress due to template change
SAM | Icost | Development | 2025-09-17 | 144 | 03 Sep - Dev in progress 17 Sep - Demo scheduled on 18 and Client demo on 19 Sep
Purushotham | Sys 2 Sys | Development | 2025-09-24 |  | 09 July - Apple Macbook in Transit 16 July - Awaiting apple connect approval for account activation 23 July - New Apple laptops is needed for Process execution, WIP 13 Aug - Scope review in Progress, SDD in Progress, Dev planned to start 20 Aug 20 Aug - Process changes are being incorporated in SDD 03 Sep - Dev in Progress, SAP test data awaited from Biz 17 Sep - On HOLD due to SAP data access 24 Sep - Development in Progress, however data access in SAP is to be enabled | SAP data access to be enabled | meeraj to enable access
Somiya P | Distressed Order | Discovery | 2025-10-03 |  | 13 Aug - Document review in Progress, 20 Aug - DB and Sap access enabled, however no test data 03 Sep - Access enabled dev planned to satrt by Friday the 05 Sep 17 Sep - Dev in progress while Solution approach is to be agreed with Business 24 Sep - Dev in progress | Test data unavailable | Wilson to provide test data for development
Sowmiya P | Vader SDE | Development | 2025-09-26 | 184 | 09 July - Apple onboarding in progress 16 July - Working on re-usable components 13 Aug - Development to completed today, demo planned on Tuesday the 19 Aug 20 Aug - Test data awaited for the demo, expecting EOD today 03 Sep - Internal demo planned today, UAT to be started 17 Sep - Demo completed - UAT likely to satrt wk starting 22 Sep upon Biz availability 24 Sepm- UAT to start today
Bhabagrahi Lenka | GS1 Registration | Hyper Care |  | 144 | 16 July - - Dev environment setup in Progress 13 Aug - SDD review awaited 20 Aug - Verbal sign off received, awaiting formal sign off, development in progress 03 Sep - Development completed, post internal demo, awaiting confirmation to start UAT on this attended automation 17 Sep - Hyper care in Progress, KT session planned with Support team today 24 Sep - KT completed to support team signof awaited from SUpport team
Bhabagrahi Lenka | GA Planning | Design | 2025-10-17 |  | 13 Aug - SDD in progress 20 Aug - awating process clarifications from BA 03 Sep - SDD completed, awaiting approval, Dev to be started this week 17 Sep - Development yet to start upon SDD approval 24 Sep - Dev in progress | Potential extension of dev completion due to complexity | Communicated to Customer
Vinay D | GA Inputs | Design |  |  | 03 Sep - awaiting biz inputs on next steps
Suresh K | Nimbus DRP Replication | UAT |  | 224 | 13 Aug - App development in progress - Blocked as on today 20 Aug - App changes being incorporated, however Nimbus application access is not enabled 03 Sep - developmnet completed, internal demo planned tomorrow 04 Sep and move on to UAT by 05 Sep 17 Sep - UAT in progress 24 Sep - UAT in Progress | Nimbus appication disclosure access to be enabled | Finance to Approve.
Suresh K | Auto GSM and FPM Capex | Discovery |  | 104 | 17 Sep - Bluebird application UI access, API access to be enabled |  | Aristo to enable the required API access Santosh to enable application access
Purushotham | APO GA Planning | Development | 2025-10-13 | 112 | 17 Sep - Development in progress, while SDD approval is waited 24 Sep - Development in Progress

## Comcast
Name | Process | Phase | ETA | Efforts Available | Remarks | Concerns | Mitigation
Akash Singhal | HRDM Virtual Work Location State vs Home & Mismatch and ABBR | Production | 2025-06-06 |  | 26 May - PDD approved 30 May - SDD Approved 20 May - Development in Progress - 70% 02 June - Dev completed 05 Jun - Dmeo given to Customer and UAT commenced 09 May - UAT in Progress, changes incorporated per the feedback from SME 16 June - UAT Completed, awaiting approval frm Biz 19 June - UAT Completed, awaiting approval frm Biz 07 July - UAT Approved KT given to Capgemini Support team 21 July - Enahancements implemenetd final UAT planned today 28 July - Prod acces to workday account is yet to be enabled for BOT 04 Aug - NO finm dates on Prod access from Security team 25 Aug - Handed Over to Comcast/ Capgemini
Akash Singhal | Taos New Hire Process | Production |  |  | 04 June - Development planned to start provided PDD is apprived by Customer 16 June - SDD approved and Dev in Progress 19 June - Code review planned today 07 July - UAT Approved KT given to Capgemini Support team 21 July - Workday access in prod envuronment to be enabled 04 Aug - UAT approved, awiating Prod deployment 25 AUg - Handed over to COmcast / Capgemini
Akash Singhal | HRDM ABBR Anniversary Files | Production |  | 104 | 15 May - SDD Completed, awaiting the model approach frm Customer, basis which SDD to be updated 21 May - SDD Approved development planned to complete 02 June UAT start to be discussed with customer 05 June - Demo given to customer 09 June - changes being incorporated, UAT to resume frm 10 June 16 June - UAT Completed, awaiting approved by Biz 23 July - NO LIve data available in Prod GO_Live, planned n 1st week of July 07 July - UAT Approved KT given to Capgemini Support team 21 July - Prod deployment to be doe b Capegemini 28 July - Yet to be deployed in Prod, awaiting Biz sign off 04 Aug - Live in Prod, Hyper care in Progress 25 Aug - Awaiting Custoemr sign off this week 01 Sep - to be handed over to Support on 05 Sep 08 Sep - - Handed over to COmcast / Capgemini
Akash Singhal | HRDM Audit Areports | Production |  |  | 07 July - PDD Approval awaited, SDD to be created post PDD Approval, Development In Progress 21 July - Dev KT to Akash in Progress -ETA - 23 July 28 July - SDD complete, to be reviewed with Sagar of Comcast 04 Aug - Development in Progress, 25 Aug - SIT in progress, UAT to start from 28 Aug 01 Sep - Dev completed, UAT likely to start by 02 Sep along with KT to be given to Comcast Support 08 Sep - KT and Code walkthourgh in progress prior to satrt of UAT 22 Sep - Deployed in Prod, ETA 25 Sep 29 Sep - New changes to be tested by Support team and complete handver by this weekend 10/03
Vamsi | Imposter Identification Process | Development | 2026-02-06 |  | 09 June - Discovery scheduled today 16 June - Feasibility for automation confirmed with SME, awaiting Biz confirmation on the next steps 23 June - Cataline - BA from US PS is creating the PDD 07 July - PDD approval waited from Biz 04 Aug - Still discovery in Progress 25 Aug - NEW BA to take up PDD from US 08 Sep - Discovery n progress 29 Sep - planned to complete PDD by 10/03 11/03 - Awaiting PDD, SDD sign off, Dev planned to start this week 12/01 - POC in progress, while PDD approval awaited 12/15 - SDD approved, deve started today
Akash Singhal | Offer letter worksatream | Discovery | 2025-12-17 | 9 | 12/01 - Discovery in Progress
| Severance workstreams Process | Discovery |  |  | 12/15 - Discovery in progress
2 more UC's inpile yet to be decided, basis the proces analysis

## Alliant Credit Union
Name | Process | Phase | ETA | Efforts Available | Remarks | Concerns | Mitigation
Rohit Rathore | BDI Staement File Exception | Prod |  |  | 05 May -UAT Completed. Waiting for UAT approval Prod deployment planned on 10 May 12 June - Prod deployment planned on 13 June 2025 19 June - Deployed in Prod 03 July - Handed ver to Customer IT team
Rohit Rathore | ACH Exception Phase I | Prod | 2025-08-01 |  | 12 June - Developent in Progress 03 July - Dev cmpleted on 30 June, UAT planned start on 07 July 10 July - UAT completed and received sign off, Prod deployment planned on 15 July 17 July - Prod deployment planned on 22 July 24 Jul - Dpeloyed in Prod on 23/07, working as expected, Hyper care in Progress 31 July - Hyper execution smooth - handed over to Customer
Rohit Rathore | ACH Exception Pkase II | Prod |  |  | 03 July - Development starting today 10 July - Development in Progress 17 July - Dev in progress 24 July - All good dev in progress 07 Aug - Code review today 21 Aug - UAT in Progress , changes being implemented 28 Aug - implemented changes and waiting test data to continue testing the changes UAT planned to compete by 05 Sep. 04 Sep - UAT completed awaiting Biz confrmation 11 Sep - Deployed in Prod on 10 Sep, Hyper care in Progress 18 Sep - Changes implemented, Biz to review and shared feedback 09 Oct - Changes implemented being tested biy Biz 16 Oct - SIgned off by Biz, Prod deployment planned on 21 Oct
Navas Hamsa | VANCO Payment Exceptions | Prod |  |  | Development in progress 12 June - Code review feedback provided by customer is being tested post implementation UAT planned to satrt by 16 June 19 June - Dev comleted, UAT planned to satrt on 23 June 03 July - UAT completed and handed over to customer IT on 26 June 10 July - Prod deployment planned today 17 July - Deplyed in Prod 24 July - Lucas is stil looking on the click of Reject button n Prod env- resolved 31 July - Hyper care in progress 14 AUg - Handed over to Customer | Hypercare
Rohit Rathore | Daily System Health Check | Prod |  |  | 03 Sep - Code enhancements in progress, UAT to resume by next week once DB access is enabled 11 Sep - UAT is blocked due to DB access for 1 module, awating Biz inputs 18 Sep - new environment being setup with new approach 09 Oct - Customer working on settip up automated DB querry run 16 Oct - Changes implemented to be deployed post automated DB Querry run by Customer 06 Nov - Module tetsing to be completed in UAT 13 Nov - UAT demo completed, change implemented and sign off awaited 11/27 - Deployed in Prod
Bhavya | Loan Trading report generation | Prod |  |  | 07 Aug - ON Hold due to intervention of Human in the Loop 14 Aug - WIP for Human in the Loop 21 Aug - Human in the Loop to be completed tomorrow and complete code review 28 Aug - Human in Loop Deployed in UAT 04 Sep - Biz meetig schedule awaited to start UAT 11 Sep - Demo scheduled today 18 Sep - Changes implemented and awaiting customer feedback 09 Sep - Planned Prod deployment today, first run on 03 Nov, as its monthly Process 06 NOv - BOT deployed in Prod and rning succesfully, 13 Nov - Prod run planned in 1st Dec
Bhavya | Apply Conserve & January Remittance | Development | 2025-12-15 |  | 14 Aug - SDD Subitted awating approval 21 Aug - SDD approval received 13 Nov - Dev in progress 11/27 - UAT application access awaited 12/11- UAT in progress, planned completion by 12/15
Bhavya | Alvaria | Prod | 2025-11-12 |  | 04 Sep - Dev planned to Complete by 08 Sep 11 Sep - Dev completed, Code review with LUcas today 18 Sep - UAT signed off, to be deployed in Prod basis Lucas availability 09 Oct - Deployed in Prod, Alvaria portal access is yet to be enabled, Sdd being updated on the approach changes required by customer 16 Oct - Smoke testing in Prod is in progress, customer feedback on change is worked out 06 Nov - Vut running successfuly in Prod, awaiting biz feedback 13 Nov - Hyper care completed, signed off by Bz
Rohit Rathore | Account Transfer | Development | 2025-12-12 | 232 | 07 Aug - Process understanding in progress 21 Aug - Dev to start after completion of ECS Phase II 28 Aug - Development in Progress 04 Sep - On HOLD, awaiting biz confirmation n next steps 11 Sep - Development to continue 18 Sep - Dev Paused due to ACH PII changes prioritized by Biz Also Scpe changes being incorporated in SDD 11/27- Dev in Progress 12/11 - Dev completed SIT delayed due to test data avalability, eta 12/12 | 11/27 - start of UAT could potentially be delayed due to un availability of test data
Bhavya | Trnsaction Code Returns Viza Payments | Development |  | 216 | 24 July - PDD, SDD review in progress, Code is partially developed by Lucas, on 31/07 code Vs SDD to be reviewed with SA and take a decission on next steps for implementation 31 July - PDD and SDD is not upto mark, needs updation - 14 Aug - ON HOLD 09 Oct - PDD, SDD approved, 13 NOv - Dev yet to be started 11/27 - Doc review in progress, dev planned to start by 01/12 12/11 - planned to satrt dev by 12/16
Jenny | Rmarketing Proceeds | SDD | 2025-11-28 |  | 14 Aug - PDD in Progress - DU Process 04 Sep - Process overhaul in discussion within Biz, post that decision on automation is awaited 06 Nov - DU architecture to be presented to customer for implementation - Yuri [TAM] and iri are working 13 Nov -ON HOLD 11/27 - SDD creation in progress, ETA - 11/28 12/11 - SDD completed, awaiting ARB approval

## Group 1
Name | Process | Project Type | Customer SPOC | Phase | ETA | PSA Efforts Available | Remarks | Concerns | Mitigations
Ponvijay Nirmal Suthakar | AP invoices | DU & Core RPA | AL Omari | Dev |  | 90 | Development Completed - ON HOLD
| OEM_Posting_AGJE | Core RPA |  | Prod
| NV_BOL | Core RPA |  | Prod
| NV_InTransit | Core RPA |  | Prod
| BRD_CDK_UUP_CRE | Core RPA |  | Prod
| BRD_AD | Core RPA |  | Prod
| DealerTrade_AU_Data | Core RPA |  | Prod
| FIC_AGJE | Core RPA |  | Prod
| RDS_Posting | Core RPA |  | Prod
| UsedCars_Purchase | Core RPA |  | Prod
| UsedCars_AAX_Process_2 | Core RPA |  | Prod
| UsedCars_Auction | Core RPA |  | Prod
| CBR_Posting | Core RPA |  | Prod
| NV_Docuware_Upload | Core RPA |  | Prod
| BRD_Docuware | Core RPA |  | Prod
| BRD_Job_Router | Core RPA |  | Prod
| Bank Email Extraction Process | Core RPA |  | Prod
| Bank_Reconciliation | Core RPA |  | Prod
| CTFlag_INVENTORY_AGJE | Core RPA |  | Prod
| HondaAcura_VehPricingDownload | Core RPA |  | Prod
| NV_DU_Cloud | DU & Core RPA |  | Prod
| NV_OCR | Core RPA |  | Prod
| UsedCars_Wholesale_Process | Core RPA |  | Prod
| BRD_CDK_ANM | Core RPA |  | Prod
| BRD_CDK_PO | Core RPA |  | Prod
| BRD_CDK_UD | Core RPA |  | Prod
| BRD_CDK_UTD | Core RPA |  | Prod
| BRD_CDKConnect | Core RPA |  | Prod
| BRD_CRM_ELeads | Core RPA |  | Prod
| BRD_DealerTrack | Core RPA |  | Prod
| BRD_Notify_Email | Core RPA |  | Prod
| BRD_RouteOne | Core RPA |  | Prod
| BRD_Xtime | Core RPA |  | Prod
| UK BMW Incentive Bonus update | Core RPA |  | Prod
| UK_BMW_Incentives_DownloadMainframe | Core RPA |  | Prod
| UK_GL_Posting | Core RPA |  | Prod
| UK_GLPosting_KeyloopDrive | Core RPA |  | Prod
| UK_Incentive_GLPosting_KeyloopDrive | Core RPA |  | Prod
| UK_Incentives_Downloads | Core RPA |  | Prod
| UK_Notify_Email | Core RPA |  | Prod
| UK_MB_Leads | Core RPA |  | Prod
| UK_RTC_Convert_Web_Booking | Core RPA |  | Prod
| UK Get Stock Number | Core RPA |  | Prod
| UK_Audi_SLI_Downloads | Core RPA |  | Prod
| UK_NewVehicle_InvoiceDownload | Core RPA |  | Prod
| UK_SLI_Kia_Downloads | Core RPA |  | Prod
| UK_UsedCar_Price_Update | Core RPA |  | Prod
| UK Delivery Receipts Validation | DU & Core RPA |  | Prod
| British Car Auction | Core RPA |  | Prod
| UK MB Download and financial Posting | Core RPA |  | Prod
Raja Christopher S | OEM_Posting_Download_and_Extraction_Domestic | Core RPA |  | Prod
| OEM_Posting_Download_and_Extraction_Hiline | Core RPA |  | Prod |  | 98
| OEM_Posting_Download_and_Extraction_Import | Core RPA |  | Prod
| US_Floorplan_Data_SFTP | Core RPA |  | Prod
| BRD_Email_Exchange | Core RPA |  | Prod
| FI_Billing_CIFF_Deals | Core RPA |  | Prod
| FI_Billing_Get_DW_Data | DU & Core RPA |  | Prod
| FI_Billing_Validation_SPs | Core RPA |  | Prod
| Term_AD | Core RPA |  | Prod
| TERM_CDKConnect_Disable_Production | Core RPA |  | Prod
| TERM_CDKUUP_Disable | Core RPA |  | Prod
| Term_CRM_ELeads_Production | Core RPA |  | Prod
| Term_Docuware | Core RPA |  | Prod
| Term_Email | Core RPA |  | Prod
| TERM_JobRouter | Core RPA |  | Prod
| CC_CreditCardPayments_New | Core RPA |  | Prod
| CDK_ADTL_REPORT | Core RPA |  | Prod
| CheckEmail_UsedCarInvoicePull_background | Core RPA |  | Prod
| US_NewParts_Process | Core RPA |  | Prod
| UK_OEM_Warranty_InvoiceDownload | Core RPA |  | Prod
| UK_PartsInvoice_Downloads | Core RPA |  | Prod
| UK_PartsInvoice_Posting | Core RPA |  | Prod
| UK_SLI_Posting | Core RPA |  | Prod
| UK_Warranty_GL_Posting | Core RPA |  | Prod
Raja | UK Audi sundry download and posting | Core RPA |  | Prod
Raja/Vijay | NewCarOEM_DL_NE&NW | Core RPA |  | Prod
Raja/Vijay | NV_Invoice_Download_Windows | Core RPA |  | Prod
Raja | UK Stripe Download | Core RPA |  | Prod
Raja | UK Stripe Postig | Core RPA |  | Prod

## Intuit
Name | Process | Phase | ETA | Customer SPOC | Work Window | Efforts Available | Remarks | Concerns | Mitigation
Santosh | ICS Auto 2821 | Production |  | Jean Pierre Cote
| ICS Auto 2981 | Production
| 1420 Business Tax | Production
| 1416 Cleanup | Production
| ICSAUTO 160 Monthly | Production
| ICSAUTO 1411 SendAnnualReport | Production
| ICSAUTO 112 SendReportPackage | Production
| ICS Auto 4952 | Production
| ICS Auto 5560 | Production
| ICS Auto 5588 | Production |  |  |  |  | 04 June - UAT planned to start frpm 05 may based on Biz availability 11 June - Awaiting Biz confirmation on UAT 09 July - Deployed in Prod, Hyper care in Progress 23 July - Hyper care cmpleted and handed over
| ICSAUTO 35 AutomatedTrainingAssignments | Production
| ICS Autom 9587 | Production |  |  |  |  | 09 July - SDD in Progress 23 Jul - UAT sign off awaited frm SME
| ICS Auto 8826 | Discovery |  |  |  |  | 09 July - Process discussion in Progress 23 Jul - PDD awaited 23 Sep - Discovery in progress
Siddappa | ICS Auto 100 | Production |  | Jean Pierre Cote
| ICS Auto 3834 | Production
| ICS Auto 2728 | Production
| ICS Auto 2984 | Production
| ICS Auto 3644 | Production
| ICS Auto 7 | Production
| ICS Auto 143 | Production
| ICS Auto 117 | Production
| ICS Auto 157 | Production
| ICS Auto 3435 | Production
| ICS Auto 5288 | UAT |  |  |  |  | 28 May - Progressing on slow pace due to SME - limited time availability 04 June - awaiting further inputs from Biz on testing & validation 11 June - Awaiting Biz confirmation on UAT 23 July - Confirmation awaited on the changes 23 Sep - Expecting some process changes, yet to be confirmed by Biz | Expecting Biz process changes, | Biz confirmation awaited on the changes to be implemented
| ICS Auto 7364 | Production |  |  |  |  | 04 June - Hyper care in Progress 11 June - BOT run is smooth no concerns from Biz 09 July - Hypercare signed off
| ICS Auto 3203 | Production
| ICS Auto 5078 | Production
| ICS Auto 9335 | Discovery |  |  |  |  | Tech assessment on HOLD due to API access 23 Jul -PDD sign off awaited 23 Sep - On Backlog now
Chaitali | 1417 Payroll Monitoring Policy | Production |  | Maaly | 2 - 10 PM IST |  |  | Dev efforts exhausted - Chaitalee Shilke New SOW Signature in Progress Start at Risk approval awaited from Samuel Mongeau
| 1344 Pin Debit Chargeback | Production
| 1244 Low Risk IUW | Production
| 1158_Financial crimes investigation | Production
| 1185_Ecommerce fraud case creation | Production
| 1169_APU EverC | Production
| 1235_Release Funds on Won Chargeback | Production
| 1148_Low Risk case automation | Production
| 1463 Nacha BOT | Production
| 1471 Payrol Collection | Hyper care |  |  |  |  | 23 July - Development in Progress 23 Sep - In Hyper care
| 1478 Capital Broker application BOT | Production
Akhila | Omni Supervrisor Scraper BOT | Development |  |  |  |  | 23 Sep - Development completed , to be used for Agentic

## Take 2 Games
Name | Process | Phase | ETA | Efforts Available | Remarks | Concerns | Mitigation
Sandeep B | Fidelity Accrual | Production | [5 empty] | 800
| Payroll UK Acrual | Production
| Jobs & Operationa Data - POC | Production
| Royality Emailing | Production
| Legal Accrual | Production
| Payroll Accrual for T2 US&CAD and Zynga US&CAD | Production
| Payroll UK Accrual | Production
| CapSw Earnings | Production
| CapSw Journals | Production
| CapSw StockComp | Production
| RPA Standalone Journal Bot | Production
| HealthCheck_LongRunning workflows | Production
| POC - Extract process submission user ID | Production
| Lease Accounting | Production
| Bupa Insurance Invoice Extract | Production
| Bupa Insurance Prepaid Journals | Production
| Street Date Deferrals | Production
| Bonus Accruals | Production
| SGG Trial Balance Upload | Production
| Capsw missing hours | Production
| CAPSW tax entries | Dev |  |  | 02/19 - Dev in progress
| FCCS Loads | Discovery |  |  | 02/19 - Techical feasibility in progress
| Inter Company Amount Trasfers | POC |  |  | 02/19 - POC presented to Finance, awaiting biz decission on implementing with UiPath Apps, Core RPA
| UiPath Apps | Dev |  | 704 | 02/19 - Building UiPath Apps for creating form to trigger process
SAM | Best Buy | Production
| Electronic Arts EA Games | Production
| Feral | Production
| Aspyr | Production
| SFDC for Zynga | Production
| Index for Zynga | Production
| Xander | Production
| Fibre Nordeus | Production
| App Lovin Nordeus | Production
| Hyper MX | Production
| Vungle Nordeus | Production
| H2 Interactive | Production
| Amazon Japan | Production
| S2GO | Production
| TAP Reasearch | Production
| Bid machine | Production
| Mintegral | Production
| RevU | Production
| GMG Homeworld | Production
| ADAPT R2- Epic_wishlist | Production
| New Ads Yeild | Production
| Scrapper Bot | Discovery
Sridhar | Concur Expense Reporting | Production |  |  | 12/18 - Enhancements being incorporated
| Microsoft backCompat sales | Production
| Royalty Load Invoice | Production
| CapSw Table | Production
| Payroll Bank statement Journals | Production
| Payroll Bank statement Reconciliation | Production
| Capsw Workday Hours | Production
| VAT B2C | Production
| Zynga Main Op Bank Reconciliation' | Production
| JDE To FCCS / JDE Cube Tie Out | Production
| Fidelity netshare reconciliation | Dev | 31 Mach 2026 | 1192 | 02/26- Dev in progress
| JD Edwards to snowflake tieout | Discovery |  |  | 02/26- Dev to satrt post complation of Fidelity
Raju Naik | MS Reconciliation process | Production
Raju Naik | Sony Asia reconciliation | Production
Raju Naik | Sony Japan | Production
Raju Naik | Sony Europe | Production
Raju Naik | Sony America | Production
Raju Naik | Apple statement reconciliation | Dev | 2026-02-20 | 928 | 02/19 - 90% dev completed, planned UAT by 02/23
|  |  |  | Name | Remaining Hrs as on 19-02-2026 | Expected End Date
|  |  |  | Sridhar Amudala | 1192 | 2026-09-28
|  |  |  | Sandeep B | 664 | 2026-06-26
|  |  |  | Raju Naik | 928 | 2026-08-12
Formulas:
Concerns = WORKDAY(TODAY(),[Remarks]/8,1)

## BJ's
Name | Process | Product Used | Work Window | Phase | ETA | Efforts Available | Remarks | Concerns | Mitigations
Megha Prabhu | Creation of RPO | Core RPA - Studio + Test Suite | 1 - 9 PM IST | Production
Megha Prabhu | Manhattan Blue Yonder TMS integration | Core RPA - Studio + Test Suite |  | Production
Durga Koushik Perumalla | Member Care with Comms Mining | Comms Mining + Core RPA |  | Production
Kumuda Sri TT | Club Roster Maintenance/Hierarchy Files | UiPath Apps+ Data Service, Core RPA -Studio |  | Production
Manoj Kumar | Hot List Report Generation | Core RPA - Studio + Test Suite+ integration services |  | Production
Manoj Kumar | Stock status reporting | Core RPA - Studio + Test Suite |  | Production
Manoj Kumar | Smart Saver Promo Validation | DU + Core RPA |  | Development | 2024-12-13
Durga Koushik Perumalla | SC Tickets in Resolve | Comms Mining + Core RPA+ Insights+Test Suite |  | Production
Kumuda Sri TT | CAB Agenda | Core RPA - Studio, Test Suite |  | Production |  |  | Handed over to BJ's Support
Megha Prabhu | Legal Litigation Task Automation | Core RPA-Studio + Test Suite |  | Discovery |  |  | ON HOLD
Megha Prabhu | On Time Truck Receiving | Core RPA - Studio, Test Suite |  | Production |  |  | 02/17 - Deployed in Progress, awaiting biz confirmation today
Manoj Kumar | Write off invoice in suspense | Core RPA - Studio + Test Suite |  | Production
Durga Koushik Perumalla | Sap Pricing / Promo | Core RPA - Studio + Test Suite+ integration services |  | Production
Megha Prabhu | Reconcile daily accident enhancement V 2.0 | Core RPA - Studio + Test Suite |  | Production
Durga Koushik Perumalla | Alarm Reporting | Core RPA - Studio + Test Suite+ integration services |  | Production
Durga Koushik Perumalla | Fuel Smart BOL Entry | Core RPA - Studio + Test Suite |  | Production
Durga Koushik Perumalla | Invoice Reconciliation | Core RPA - Studio + Test Suite |  | Production
Manoj Kumar | Pumps Down Reporting | Core RPA - Studio + Test Suite |  | Production
Durga Koushik Perumalla | Fuel Pump inactivity Alert | Core RPA - Studio + Test Suite |  | Production
BJs Developer | PlayerLync Reporting |  |  | Hyper Care |  |  | Delayed due to continued changes
Sushmita Dey | BI Perishable Process |  |  | Production
BJs Developer | Legal Document Search | Context Grounding+A4E |  | POC |  |  | POC in progress By BJ's develoepr, guided by Vasanth SA
Durga Koushik Perumalla | Resume Screener | Core RPA - Studio + Context Groundig+ IS + Gen AI + Apps |  | Production
Sushmita Dey | Aged Inventory Process |  |  | Production
Kumuda Sri TT | Absent and late tracking |  |  | UAT |  | 40 | 03/06 - discussion scheduled tomorrow on the process design
Kumuda Sri TT | Fuel Alarm Reporting: | Core RPA - Studio + Test Suite +Insights |  | Production |  |  | Handed over to Support
Durga Koushik Perumalla | Email parsing and ticket creation | Comms Mining + Core RPA+ Insights+Test Suite |  | Production
Megha Prabhu | BI Perishable Process V2 |  |  | Production
Durga Koushik Perumalla | DC end of shift 820 | Core RPA+Test Suite |  | Development | 2025-02-20 |  | 02/17 - Feedback awaited from SME
Sushmita Dey | DC end of shift 840 |  |  | Discovery |  |  | 03/03 - PDD in progress
Sushmita Dey | DC end of shift 800 |  |  | Discovery |  |  | To Be Taken after 820
Durga Koushik Perumalla | Vendor Onboarding POC |  |  | POC |  |  | POC Completed
BJs Developer | Class Compliance |  |  | Discovery |  |  | Development in Progress
Kumuda Sri TT | Open Shft Process |  |  | Development |  |  | 03/03 - to be taken up post DC Bill of Lading completion - Status to be udpated post discusssion with PM
BJs Developer | Missing and Open Receipts |  |  | Development |  |  | PDD approved in development
Shlok | Cash Varience |  |  | Development |  |  | 03/03 - dev completed, UAT likely to start by 03/06
Durga Koushik Perumalla | Special Order Tire Stickers | Core RPA |  | Production |  |  | Live in Prod
Megha Prabhu | Exporting from EP |  |  | Development |  |  | 03/03 - test creation in progress
Sushmita Dey | Consolidated Reporting |  |  | Discovery |  |  | 03/03 - PDD in progress
Sushmita Dey | Ticket Mate |  |  | Discovery |  | 201 | 03/03 - to be re-piroritized by Biz
Kumuda Sri TT | DC Bill of Lading |  |  | Production |  |  | 03/03 - Deployed in Prod
Sushmita Dey | Ariba Facilitator |  |  | Discovery |  |  | 03/03 - to be discussed with SA dn Biz on the design
Shlok | CAB Agenda 2.0 |  |  | Production |  |  | 03/03 - deployed in Prod, potential enhancement anticipated
Megha Prabhu | Export from EP |  |  | Development | 2026-03-23 |  | 03/03 - Dev in progress, Despatcher completed Performer in progress
Sushmita Dey | DC Bill of Lading - Vendor name updation |  |  | Discovery |  |  | 03/03 - PDD in Progress
Sushmita Dey | Email Parsing creation Phase II |  |  | Discovery |  |  | 03/03 - requirement gathering completed
Sushmita Dey | Product reviews safety concerns |  |  | Discovery |  |  | 03/03 - PDD in progress
Sushmita Dey | Freight claim processing |  |  | Discovery |  |  | 03/03 - PDD in progress
Sushmita Dey | Cash Variance |  |  | Discovery |  |  | 03/03 - test creation in progress

## Houston Methodist Closed
Name | Process | Phase | ETA | Efforts Available | Remarks | Concerns | Mitigation
Sachdeep Singh | Time card1 | Prod |  |  | 21 May - Test case documentations completed and sign off received 22 May - Development in progress as per schedule 29 May - Client demo today 12 June - UAT in Progress, delayed by 4 days due to application outage ETA to complete by 18 June 19 June - UAT to be resumed today 10 July - New set of records provided, needs UAT to be continued 24 July - Deployed in Production, smoke testing today 31 July - Cosmetic changes implemented in Prod and BOT run successfull
Sachdeep Singh | Time Card 2 Expansion | Prod |  |  | 12 June - Development in Progress 19 June - Demo planned om 26 June 10 July - UAT to be continued 24 July - UAT in Progress, with minor e-mail formating changes being implemented, UAT sign of expected by mnday the 28/07 31 July - UAT sign off awaited from SME 07 Aug - changes implemented awaiting user confirmation 14 Aug - Deployed in Prod, 2 KT's given to customer 21 Aug - Handed over to customer
Sachdeep Singh | Drug Screening | UAT | 2025-08-29 | 89 | 10 July - Dev in Progress 24 July - Dev planned to completed by 04/08 - , Awaiting SME confirmation on Biz Logics 07 Aug - Development in progress 14 Aug - Development planned to complete by 19 Aug, enhancement being updated in PDD, SDD 21 Aug - Feedbacks being implemented
Shubham Jadhav | Staff Scheduling | Prod | 2025-08-17 | 49 | 22 May 2025 - Development scheudled impacted due to these 2 days of app access outage 29 May - Dev in progress as per schedule 12 June - Dev delyed due to application down - 4 days [3-9] Client demo planned on 18 June 19 June - Demo reschuled on 20 June, due to labor worx app outage 10 July - UAT in Progress 24 July - Code deloyed in Prod, smole testing today 31 July - Prod env issues fixed and BOT run being monitored, next run is only on 17 Aug
Shubham Jadhav | Physician Affiliation | UAT | 2025-08-29 |  | 19 June - Dev planned to start by 24 June 10 July - Dev in progress 24 July - Dev in Progress 31 Aug - Dev in progress, completion on 08 Aug 07 Aug - Dev in progress 21 Aug - demo planned today, UAT planned to satrt by 22 Aug and close by 29 Aug
Syed Abdhahir | Cash Recon | Prod | 2025-08-01 | 68 | Dev completed, Integration in Progress Demo Pllaned on 27 May 20 May - Test case documentations completed 12 June - Changes are implemented, UAT planned to start today 19 June - changes deployed and awaiting biz confirmation 10 July - UAT completed, Live planned on 24 July - Code deployed in Prod 31 July - BOT running successfully in Prod
Syed Abdhahir | EFT DU Despatcher | Dev | 2025-09-12 | 220 | Development temporarily on Hold will resume once Cash Recon is completed 10 July - Training of docs in Progress [700docs] - DU part in Progress 24 July - DU Process 90% completed, first cust feedback, customer confirmed as expected 31 July - complete development by 31 July and start Performer RPA Bot 07 Aug - Despatcher completed
Syed Abdhahir | EFT Performer | Dev | 2025-08-05 |  | 24 July - Test case doc prepartion in progress 31 July - planned to complete by 05 Aug 07 Aug - Performer development in progress 21 Aug - Performer dev in Progress | 21 Aug - VM performance - slowness is impacting the development | communicated to PM and customer
Veera | Physician Affiliation | SDD |  | 53 | SDD walkthrough on 16 May Conpleted 22 May - Feedbacks being incorporated 12 June - SDD sign off received Test case documenta shared with customer, feedback awaited 19 June - Test case doc signed off
| Drugs Screening | SDD |  |  | 12 June - Walkthourgh completed, customer feedbakc awaited 19 June - SDD and Test case do signed off
| Time card1 |  |  |  | 12 June - Code reiew in progress 19 June - Code review completed
| Time card 2 |  |  |  | 12 June - Test case doc in progress 19 June - Test case doc signed off, however work in progress on the feedback 24 July - 2nd round code review completed

## Tokyo Closed
Name | Process | Phase | ETA | Efforts Available | Remarks | Concerns | Mitigation
Rajagopal | Tokyo Pack Slip Generation | Prod | 2025-08-29 |  | 25 July - Dev in progress,Changes being incorporated, to be closed by 28 July 01 Aug - Sap credentials and access enabled today, UAT planned to satrt by 05 Aug, awaiting test data 22 Aug - UAT completed, awaiting customer sign off for Prod movement planned next week 28 Aug - SMoke testing is already in Progress, Awaiting Biz approval on Prod Sign off,
Krupa Pujilala | SalesOrder Entry | Hyper Care | 2025-08-29 |  | 25 July - Dev targetted to complete today, Internal demo and UAT to start on 28 July 01 Aug - Dev SAP testing to be done today, UAT likely to satrt by 05 Aug , 22 Aug - UAT completed, go-Live planned today 28 Aug - Hyper care in Progress 05 Sep - Awaiting customer sign off, while BOT runs are succesfull
Krupa Pujilala | Supplier Managed Inventory | Dev |  | 157 | 05 Sep - Development in Progress SAP access alone nebaled, awaiting other app access 12 Sep - 30 Sep Dev planned to connect

## CAMC Vandalia Health Closed
Name | Process | Phase | ETA | Efforts Available | Remarks | Concerns | Mitigation
Sathish P | Claim Status Report | Hyper Care | 2025-09-03 | 36 | 10 April Startted development 03 June - Planned dev compeltion 13 June - UAT Planned completion 16 May - SDD Approved 09 June - Demo planned & Completed 16 June - UAT progressing well 23 June - UAT completed , 2 SME approved, 1 SME awaited , Code Run book and MTP documentation in progress, PROD environment setup in Progress 07 July - UAT Cmpleted and Deployed in Prod 28 July - PROD run from today 04 Aug - Chnages being incorporated by AMal and Sathish 25 Aug - CHanges implemenetd and deployed in Prod, 2 -3 BOT runs to be done to monitor the Performance and then seek SIgn off 01 Sep - 2 more of days of HC on changes implemented 22 Sep -Handover planned to support today
Sathish P | Denials Itemized Process | Hyper Care | 2025-09-10 | 160 | SDD completion delayed due to customer training, as they are new to RPA 22 May - SDD shared for approval, review completed, ETA 30 May 29 May - SDD Approved 09 June - Planned alloaction to Satish after completin of Process 1 07 July - Dev in Progress 14 July - Dev in Progress, awaiting test cases from customer 28 July - Test data awaited 25 Aug - Unit testing completed, Test data awaited to start UAT 01 Sep - resuming development of 5% from today, received test data 08 Sep - UAT In Progress 22 Sep - Hyper care in progress, enhancements in progress, planned closure by 29 Sep
Abhishek Singh | Access Edit Patients - Despatcher | Dev | 2025-05-14 | 158 | 16 May - SDD Approved Despatcher Part Completed
Abhishek Singh | Access Edit Patients - Performer | Hyper care |  |  | Performer development completed 16 June - Demo Planned on 19 June with the available data 19 June - Demo completed, new requirements being incorporated asper PROD environment 07 July - UAT to be completed today 14 July - UAT completed, smoke test today in Prod 28 July - Code Sanity n Progress, Amal to suport 04 Aug - Hyper care in Progress, while changes are being implemented 25 Aug - Implementing chages 01 Sep - Changes implemented and awaitig HC sign off 08 Sep - Awaiting SIgn off 22 Sep - Changes being implemented by 25 Sep, 48 WD bot run successful | Test Data dependency | Jordan to provide test data
Abhishek Singh | Charge Line Rendering | Hyper Care |  |  | 16 June - Development planned to start by 17 June 23June -ON Hold due to CR's in Access Edit patients Performer 07 July - ON HOLD 04 Aug - Development in Progress, ETA - 01 WK Sep 25 Aug - Unit Testign in progress, blocked due to test data 01 Sep - SIT in progress, UAT to staart from 03-Sep 08 Sep - Awaiting formal sign off in e-mail, verbal sign off received, Smoke tetsing started today 22 Sep - To be handed over to support by 24 Sep
Chetan D | Access Edit Camc - Despatcher | Prod | 2025-07-08 | 37 | 16 May - SDD Approved Despatcher Part Completed
Amaladeepan | Access Edit Camc - Performer | Hyper care | 2025-09-04 |  | Performer development 16 June - Slight change on summary report is being incorporated, demo planned on 19 June 23 June - Demo completed, UAT in progress 07 July - UAT completed including the changes requested, Prod deployment planned 09 July 14 July - UAT completed, smoke test today in Prod 28 July - Standardization in progress for Insights 04 Aug - Hyer care in Progress, Insights customization in progress 25 Aug - Changes being implemenetd by Amaladeepan 01 Sep - Canges implemented and being tested internally 08 Sep - Awaiting formal e-mail sign off, verbal sig off received 22 Sep 48 WD BOT run successfull, to be handed over to support by 25 Sep
Chaman | Phase II Discovery in Progress -5 Use cases | Design |  | 102 | 23 June - As per inputs frm Sales, we hall wait till 30 June on the customer response to resume the Scoping and estimation 07 July - Fruther udpates awaited from customer, likely in next 1 week 04 Aug - Phase II discovery approval waited from leadershipto start discovery 01 Sep - Upon completion of PHase I, ROI, Phase II to be decided
Amaladeepan | Claim Status UHC | Dev | 2025-09-12 |  | 25 Aug - Development in Progress 01 Sep - 15% development completed 08 Sep - 25% dev completed 22 Sep - 40% dev completed, ETA Oct end

## Homeserve Closed
Name | Process | Phase | ETA | Efforts Available | Remarks | Concerns | Mitigation
Dharunya Devi | Email templates | Prod |  | 237 | 25 July - Hyper care in Progress 01 Aug - New Pop up in prod is impacting the BOT run, awaiting inputs from SME 22 Aug - Awaiting Biz Sign off 29 Aug - Signed off by Biz
| Bank Vs GL | Prod | 2025-09-10 |  | 25 July - Dev in progress 22 Aug - UAT in orogress, whle changes are being incorporated ETA 22 Aug 29 Aug - Prod Go-Live today, hyer care planned b/w 1 to 5 Sep and KT
Mina Mundhe | Email templates | Prod |  | 290 | 25 July - Hyper care in Progress 01 Aug - New Pop up in prod is impacting the BOT run, awaiting inputs from SME - 01 Aug, expecting Biz to show us the Pop up to handle them in BOT 22 Aug - Awaiting Biz Sign off 29 Aug - Signed of by Biz

## Zscaler -Closed
Name | Process | Phase | ETA | Efforts Available | Remarks | Concerns | Mitigation
Sarita Shukla | SFDC Ticket E-mail Automation | UAT | 2025-08-12 |  | 24 July - development and testing in progress, 31 July - Testing in progress on the exception handling steps 07 Aug - Development and Internal testing completed, UAT to start, post demo on 12 Aug 14 Aug - Testing in Progress by ops team 21 Aug - BOT Access in prod in unavailable, expected mid of Sep, Awaiting new process for development from Varchasv 28 Aug - Feedback awaited from Biz
| T&E Corp CC Accruel | Discovery | 2025-09-12 | 112 | 22 Aug - Requirement gathering in progress 28 Aug - Development in Progress 04 Sep - Customer is re-thinking on the solutionig and temporarily on HOLD
| T&E Citi Bank Reconciliation | Discovery |  |  | 04 Sep - Discovery in Progress
| Deffered Revenue | Dev |  |  | 04 Sep - Changes being incorporated

## Workday- Closed
Name | Process | Phase | ETA | Customer SPOC | Work Window | Efforts Available | Remarks | Concerns | Mitigation
Ekta | Corps Accounting | Production |  | Veera Boddula | 1 - 09 PM IST |  | Deployed in Production and signed off on 26 Nov 2024
Nishi Singh | AP process | KT | 2024-11-05 |  | 1 - 09 PM IST |  | KT completed to Workday
| Rev OPS - Subscription - Nishi / Ekta | Production |  |  |  |  | Deployed in Production, Hyper care sign off awaited
| Rev OPS - Training - Nishi / Ekta | Production
Phase 2 | Rev OPS - Subscription - Nishi / Ekta | Production
Phase 2 | Rev OPS - Training - Nishi / Ekta | Production
Ekta | PSA expert Assist | UAT | 2025-07-10 |  |  |  | UAT in Progress, Prod deployment planned on 10 July | SIT could not be completed due to delayfrom other developer - Gilbert | PM - Ammar is aware of limited SIT
Nishi Singh | PSA Sub contractor | Production |  |  |  | 71 | Deployed in Prod on 02 July, 2 weeks Hyper care planned

## Fresenius- Closed
Name | Process | Brief Process Description | Phase | ETA | Customer SPOC | Work Window | Migration Use case | Efforts Remaining | Remarks | Concerns | Mitigations
Nikita | NA GBS P2P R-Block Reports |  | Delivered |  | Kevin Rodrigues |  | BP to UiPath |  | 12 .30 - 9.30 PM IST Work Timings
Efforst remaining 444 | NA GBS P2P Invoice and Payments Notification |  | Delivered |  |  |  | BP to UiPath
| NA CORP AR TruBlu Invoices |  | De-Scoped |  |  |  | BP to UiPath |  |  | Descoped after dev was half way through
| NA Cycler RGA Report |  | Delivered |  |  |  | BP to UiPath
| NA CORP CLA Reconciliation |  | De-Scoped |  |  |  | BP to UiPath |  |  | BRD and UAT Sign off not available
| GLOBAL GBS SFTP Blackline |  | Delivered |  |  |  | BP to UiPath
| APAC FME GBS Fixed Assets Reporting Insite | BOT will extract Asset Histrory, Asset serial number, Asset Profit Center , Plant IO , Depreciation Simulation , Asset Retirement, , Financial Statement from SAP and update the file location path in Power Query Template and save the template Application used Outlook, Excel, SAP | UAT |  |  |  | BP to UiPath |  | Biz sign off expedt by 17 Jan 2025 | "1. Delay in receiving updated power query file and SAP steps 2. Multiple UAT rounds performed despite no issues in bot run during positive and negative testing, due to Power query issue. Previous month files to be used for testing provided in a different format than required and developer had to recreate files with current template resulting in additional time for re-testing, which was not taken into consideration"
| GLOBAL GBS TP Engine | In this process bot will check the files uploade in Sharepoint by TP Engine. Compare the no of posting and document number generated in SAP, lastly Upload the PDF document in SAP. Application used - Outlook, Excel, SAP | Delivered |  |  |  | BP to UiPath |  | KT completed - Jovie Mae De Guzman, Jhimben Gonzales, Dexter Amor
Nikita | APAC FME SSC Bank Reconciliation | BOT to download 4 SAP reports for MAIN< INCOIMING, OUTGOING, FEBAN.update the Power query template with report details and save the power query template. Application used - Outlook, Excel, SAP | De-Scoped |  | Kevin Rodrigues |  | BP to UiPath |  | After completion of UAT, Customer de-scoped this proces stating biz is no more using this Process | Customer is yet to fix the power Querry
| NA Cycler and Tanks Capitalization | In this process bot downloads 4 different SAP Reports based on the input provided in the config file. Save the SAP files to a shared folder location and update the file path in the power query template and refresh the query. Application - Outlook, Excel, SAP | Delivered |  |  |  | BP to UiPath |  | KT completed - Jovie Mae De Guzman, Jhimben Gonzales, Dexter Amor
| NA FME RTG 50B Downloads | In this process bot will download Matrix file from Blackline API . Get the Spool request number from SAP and download the pdf from SAP (SP01). Save the PDF with file location and file name based on matrix file and send an email upon completion of the process. Application used - Outlook, Excel, SAP | Delivered |  |  |  | BP to UiPath |  | KT completed - Jovie Mae De Guzman, Jhimben Gonzales, Dexter Amor
Shreshta | EMEA – FME SSC Proof of Delivery |  | De-Scoped |  |  |  | BP to UiPath |  | De-Scoped from automation due to sensitive data involved in the process
Krupa Pujilala | Creation of BOT to Close PO Limits | Bot to download PO Limit Data from SAP, send the file to business team for approval on each row in the excel.Business team to respond back to the same email with the updated excel. Bot to read the excel. Open SAP and check the status of approved PO , if mentioned criterias matches in SAP lock the PO. Application used Outlook, Excel, SAP | UAT |  | Ramya G |  | New Implementation | 264 | Bharthi awaiting internal approval for Prod Deployment from 24/02
Nikita | NA Fixed Assets |  | Development |  |  |  | BP to UiPath | 196 | Insjght access and input files missing - Kevin to enable |  | Kevin and Bharthi are aware of the challenges
Chaitanya | Info record Update | The process first determines whether the material already exists in SAP based on the type of request that was received from the business in the form of an Excel document. If not, it must build the material and then update or modify the material information based on the request type. Application Used – SAP , Excel , Outlook | Development |  |  |  | New Implementation | 72 | Application credentials awaited from Shamsala 14/03
Navas | Phy Comp setup of recurring payments | The shared drive contains the Contract Analysis Template, which needs to be changed with the document number produced by SAP for the recurring payment by running the FBD1 T-code. Use the ZFPA T-code to get the Recurring Entry document. Additionally, copy and paste every document screenshot into the ZFPA template. Application Used – SAP , Excel , Outlook | Development |  |  |  | New Implementation | 104 | SP Path is not created yet - Shamsala 14/03
Krupa Pujilala | Celonis Write Back |  | Discovery |  |  |  |  | 191 | SAP Access awaited 14/03
Nikita | Bank Recon Wave 5 |  | Discovery | [5 empty] | Pre-requisotes shared today 13/03, estimates to be prepared 13/03
Shreshtha
Sivasankari

## Vialto- Closed
Name | Process | Phase | ETA | Efforts Available | Remarks | Concerns | Mitigation
George | AMCA_TX_MEX_Refund_Status_Check | Production |  | 379
George | AMCA_TX_MEX_Tax_Information_Download | Production
George | EMEA_TX_NOR_Questionnaire_to_Capego_Data _Transfer | Production
George | EMEA_TX_BEL_Billie | Discovery
George | AMCA_TX_MEX_Tax_Inbox_Review | UAT
Ranjith | AMCA_TX_MEX_eFiling | Production |  | 440
Ranjith | AMCA_IM_CAN_LCA_All_Client | Production
Ranjith | APAC_TX_PHL_PayslipPlotting | Production
Ranjith | EMEA_TX_LUX_Luxat_Salary_Import | UAT
Ranjith | EMEA_TX_BEL_SAP_BRS_Clearing | Development

## Tenet Closed
Name | Process | Customer SPOC | Work Window | Phase | ETA | Efforts Available | Remarks | Concerns | Mitigations
Adavelli Anusha / Shlok | Hospital AR Reports process | Shashi | 1.30 - 10 PM IST | Production |  |  | Changes implemented, to be deployed in 1st week of December
| Fixed Assert Retirement process | Shashi |  | Production |  |  | Deployed in Prod, sanity test completed, | Password Pop up issue blocks BOT execution, | Soln to be confirmed by Tenet IT
| Fixed Assert Transfer process | Shashi |  | Production |  |  | Deployed in Prod, sanity test completed, | Password Pop up issue blocks BOT execution, | Soln to be confirmed by Tenet IT
Karthik Deshpande | Initiating Payment Runs in Oracle | Shashi | 1.30 - 10 PM IST | Production |  | 382
| Managing Payment Runs in Oracle (ACH & CHK) | Shashi |  | Production
| CFO Revenue Process | Shashi |  | Production
Shlok Singh | Creating New Vendors proces [DU] | Shashi | 1.30 - 10 PM IST | Prod |  | 222 | Deployed in Prod
Prod deployment planned on 21 Jan 2025
| Invoice Entry - PO Process |  |  | Development |  |  | Development in Progress Shlok Working on DU Part - 19-Jan-25 Karthik wokring on Non DU part Additional automation to be enabled, for which requirement gathering in progress | Certain querries and data requested frm Business are delayed, that might potentially impact the delivery schedule | Impact escalated to Project Manager - Ammar as well to customer to
| Invoice Entry - NON PO Process | [5 empty] | Likely to start in last week of Feb '25
82368

## RWJBH Closed
Name | Process | Customer SPOC | Work Window | Phase | ETA | Efforts Available | Remarks | Concerns | Mitigations
Sivasankari | Prior Auth Detemination | Jessica | 02- 10 Pm IST | Production |  | 100 | Hyper care in Progress, BOT execution smooth
Pavithra Anandan/ Sivasankari | Prior Auth Status | Susan/Fallon | 02- 10 Pm IST | Production | TBD |  | bug fix for portal and epic going on
Shreya Shrivastava | Notice Of Admnission | Cara Tompkins | 02- 10 Pm IST | Production |  |  | CR implemented in Prod, smoke tetsing likely on 22/01
Sivasankari s | Medical Records | Linda Bilek | 02- 10 Pm IST | Dev Completed |  |  | RWJBH is owning this process, due to biz reasons
Project tentively to be completed by 03 Feb

## DOW Closed
Name | Process | Phase | ETA | Efforts Available | Remarks | Concerns | Mitigation
Shijin | UK PECI Automation | Production
Liri |  |  |  | 23.5 | Go-Live expected by 09 Aug
[5 empty] | Biz statement - Only post BOT generated results, Biz will decide on the scope and Changes | Scope freezed and additional efforts [CR] shared with customer awaiting signature
| EID Checks | Discovery |  |  | PDD creation in Progress
| Play Planning Data Audits | Development | 2024-09-16 |  | Development in progress Test cases being prepared | Awaiting access to be enabled for MS Access, in UAT and Prod environments. Dev in progress - as per schedule

## Exelon Closed
Name | Process | Customer SPOC | Phase | ETA | Efforts Available | Remarks | Concerns | Mitigations
Purushutham | 496 CCB Report Validation - Despatcher | Christy Bartlett | UAT |  | 240 | UAT signed off, awaiting CCB approval for Prod deployment
AT present BOT is scheduled to run everyday in UAT and sending daily reprts to Biz SME
Biz requested to replicate the exiting type of report to mutiple type of repoorts
Prakhar | 496 CCB Report Validation - Performer | Christy Bartlett | UAT |  | 202 | UAT signed off, awaiting CCB approval for Prod deployment
Biz requested to replicate the exiting type of report to mutiple type of repoorts
Shailendra | 493 Flat File Process |  | SDD |  | 281 | PDD completed , review scheduled with Biz 10/09 | SDD will satrt post PDD sign off
Application access yet to be enabled to start development
Sail Point, Service Now and Shared drive access to be enabled
| 479 SIRT Roaster |  | PDD
Sanjana | 492 Mesh Survey - DU Use case |  | PDD |  | 192 | PDD completed , review scheduled with Biz 10/09

## NYPA Closed
Name | Process | Customer SPOC | Phase | ETA | Efforts Available | Remarks | Concerns | Mitigations
Dharunya | AP Inquiries | John.Wagner@nypa.gov;Emmanuel.CHERIAN@nypa.gov | Hyper Care |  | nFDS 112 | Hyper care in Progress, KT Completed
| SAP Reports | sameer.thakur@nypa.gov | Production |  |  | Hyper care Signed off, KT completed
| Tech Scouting | subbulakshmi.subramaniam@nypa.gov, Marwan.madi@nypa.gov | Production |  |  | Hyper care Signed off, , KT completed
| HR process(Canals data entry) - | jolie.chong@nypa.gov; angimar.mosqueda@nypa.gov | Development |  |  | Despatcher completed Performer is stuck due to unavailability of SAP access | SAP access not enabled for development and testing | Escalated to PM and customer
| E- Mobility | Raphael.Gernath@nypa.gov; | UAT | 2025-02-07 |  | UAT In Progress | Graph API to be enabled for e-mails
| LMS Enrollment Report |  | Development |  |  | UAT Planned to satrt by 07 Feb 2025