## Issue Description
Customer | Issue Type | Count | Percentage
| Yes | 1 | 1.887% | Customer | Risk | Mitigation
HUB International MS | The lead from WBZ is not up to the mark and few escalations happened. Replacing this lead. Way forward discussed and agreed with the customer along with AE |  |  | JPMC Migration | Objective : JPMC existing 22.04 standalone Orchestrator is to be migration to 23.10 Automation Suite RISK - This is large scale migration | Working closely with Product team and TAM Step 1: 22.4 Standalone Orchestrator (JPMC) database to 23.10 Standalone (UiPath Test Instance) Step 2: 23.10 Standalone (UiPath Test Instance) Full Migrate to 23.10 Automation suite (JPMC new Instance)
HUB International | Product Issues - Gen AI Extraction for Table and Checkboxes. This prevents Go-Live
| No | 52 | 98.11%
| Grand Total | 53 | 100%
PS Note - This is only a reference Snip - FYI only

## Phase wise count
| Total | Discovery | Dev | UAT | Hyper care | Prod | Sl. No | Project Name | Active Engagements
JPMC | 3 |  |  |  |  | 3 | 1 | BJ's Wholesale Club-Hybrid-100% discounted-Service Credit Prepaid-PR-005394 | 1
Amazon Music | 3 |  |  |  |  | 3 | 2 | Amazon-Business 2 Busi-Fixed Price-POD-008831 - Music | 1
Deloitte AUS AA | 6 | 2 | 1 |  |  | 3 | 3 | Group 1 Automotive-Time and Materials-Prepaid-010186 | 1
Deloitte GM | 3 |  |  |  |  | 3 | 4 | Lydonia Te-America Fujiku-Time and Materials-POD-009156 | 2
Deloite SF | 4 | 3 |  |  | 1 |  | 5 | Lydonia Te-USI Service Co-Time and Materials-POD-008284 | 1
Group 1 | 79 |  | 1 |  |  | 78 | 6 | Deloitte Global Services-Hybrid-Service Credit Prepaid-PR-008208 | 3
CAMC Vandalia | 9 | 1 | 2 |  | 5 | 1 | 7 | Intel Corporation-Time and Materials-POD-009522 | 2
Intuit | 38 | 2 | 1 | 2 | 1 | 32 | 8 | Intuit Inc.-Time and Materials-Prepaid-PR-008662 | 2
Tokyo Electron | 3 |  | 1 |  |  | 2 | 9 | Lydonia Te-Angelo Gordon-Time and Materials-POD-009816 | 1
Take 2 | 51 | 2 | 1 | 2 |  | 46 | 10 | Take-Two Interactive Soft-Time and Materials-Prepaid (PR-010307) | 3
Citizens | 40 | 5 | 3 | 7 | 1 | 24 | 11 | Citizens Bank National A-Fixed Price-100% disc.-Service Credit Prepaid-008086 | 1
BJ | 39 | 11 | 5 | 2 | 2 | 19 | 12 | JP Morgan Chase(Global-Fixed Price-Service Credit Prepaid-100% Discounted-008300 | 1
HUB | 13 |  | 5 | 2 |  | 6 | 13 | Massachusetts Mutual Life-100%discounted-Service Credit Prepaid-008575 | 1
Intel | 33 |  | 3 | 3 |  | 27 | 14 | Hub International-Time and Materials-POD-009736 | 3
Houston | 10 | 2 | 4 |  | 1 | 3 | 15 | MGM Resorts International-Fixed Price-Prepaid-009499 | 1
Homeserve | 12 | 9 |  |  |  | 3 | 16 | CAMC Health System-Hybrid-POD | 1
Alliant | 12 | 4 | 2 | 2 |  | 4 | 17 | The Promptcare Companies-Fixed Price-100% DISC-Prepaid-009890 | 2
Promptcare | 6 |  | 4 | 1 |  | 1 | 18 | Homeserve USA-Fixed Price-Prepaid-009745 | 1
icertis | 1 |  | 1 |  |  |  | 19 | Houston Methodist Hospita-Hybrid-Prepaid-100% Discounted-009695 | 1
Wabtec | 1 |  | 1 |  |  |  | 20 | Comcast (Cable Communicat-Fixed Price-Prepaid-009360 | 1
Comcast | 5 | 1 |  |  |  | 4 | 21 | Alliant Credit Union-Time and Materials-POD-009664 | 1
Onity | 1 |  | 1 |  |  |  | 22 | PepsiCo Inc-Service Credit-100% Discounted-009972 | 1
AFL | 6 | 2 |  | 1 | 1 | 2 | 23 | Lydonia Te-Snap-On Credit-Time and Materials-POD-PR-009958 | 2
USI | 3 |  |  |  |  | 3 | 24 | Tokyo Electron U.S. Holdi-Fixed Price-Prepaid-008051 | 1
Snap On 1 | 11 |  |  |  |  | 11 | 25 | Onity Group Inc-Fixed Price-Prepaid-010078 | 1
Snap On 2 | 7 |  | 2 |  |  | 5 | 26 | Zscaler Inc-Hybrid-Service Credit-Prepaid-100% Discounted-009841 | 1
AG | 27 |  | 2 | 2 |  | 23 | 27 | Apple-Fixed Price-Service Credit Prepaid 100% Discounted-PR-010148 | 1
Pepsi Co | 198 |  | 3 |  |  | 195 | 28 | FinThrive Revenue Systems-Hybrid-Service Credit Prepaid-100% Discounte-PR-009904 | 1
FinThrive | 1 |  | 1 |  |  |  | 29 | Equifax Agentic | 1
Zscaler | 2 |  | 1 |  |  | 1 | 30 | Amazon - Global Freight P-Fixed Price-Prepaid-009950 | 1
Avista | 1 | 1 |  |  |  |  | 31 | Icertis Inc.-Fixed Price-Service Credit Prepaid | 1
Apple | 15 | 5 | 6 |  | 2 | 2 | 32 | Amazon - TSI Automation (PS) | 1
Liberty | 1 |  | 1 |  |  |  | 33 | Avista Corporation-Fixed Price-Service Credit Prepaid-100% Discounted-PR-010219 | 1
Equifax | 1 |  | 1 |  |  |  | 34 | Western Alliance Bank-Time and Materials-Prepaid-100%Disc-010592 | 1
Amazon GF | 3 | 3 |  |  |  |  | 35 | Johnson Controls Inc. JCI - PS for Field Service Q-898052 V.6 - DU (using GenAI Extraction) | 2
MGM P1 | 1 |  |  |  |  | 1 | 36 | Wabtec Corporation-Fixed Price-POD Project ID PR-009839 | 1
MGM P2 | 1 | 1 |  |  |  |  | 37 | The Standard-Time and Materials-Prepaid 100% Discounted-010322 | 1
WAB | 1 | 1 |  |  |  |  | 38 | Edgewell Personal Care Br-Fixed Price-Service Credit Prepaid-100% disc_PR-010064 | 1
CS University | 1 | 1 |  |  |  |  | 39 | DENSO International Ameri-Time and Materials-Prepaid-010394 | 2
Skanska | 1 |  | 1 |  |  |  | 40 | Micron | 1
[7 empty] | 41 | Voya Services Company-Time and Materials-POD 010485 | 1
Total | 653 | 56 | 54 | 24 | 14 | 505 | 42 | Lydonia Te-Falvey Insuran-Time and Materials-POD-010347 | 1
[6 empty] | 72 | 43 | FMC Corporation-Time and Materials-POD-010491 | 1
| 725 | 56 | 54 | 24 | 14 | 577 | 44 | Liberty Mutual Insurance-Hybrid-Service Credit Prepaid-100% Discounted-005449 | 1
[7 empty] | 45 | Bank of America (Global)-Time and Materials-Prepaid-010590 | 1
[7 empty] | 46 | Skanska USA- Fixed Price-Prepaid- 100% DISC-010503 | 1
[7 empty] | SL. NO | No of Customers | Nof Projects | SOW Type | Status | UIPath | CW | Total
[7 empty] | 1 | 45 | 58 | AMER | In Progress | 30 | 74 | 104
[7 empty] | 2 | 9 | 9 | AMER | Yet To Start
[7 empty] | 3 | 7 | 7 | MS | In Progress | 3 | 26 | 29
[7 empty] | Total | 61 | 74 |  |  | 33 | 100 | 133

## Resources allocations
Project | Developer | BA | SA | PM | Infra Engg | Allocated On
Murphy Oil | 1 |  |  |  |  | 2025-06-03
MassMutual |  |  | 1 |  |  | 2025-06-05
Zscaler | 1 |  |  |  |  | 2025-06-06
Wells Fargo | 1 |  |  |  |  | 2025-06-09
JPMC | 2 |  |  |  |  | 2025-06-09
Apple | 2 |  |  |  |  | 2025-06-11
Finthrive |  |  | 1 |  |  | 2025-06-11
Amazon Global Freight | 2 | 1 | 1 | 1 |  | 2025-06-17
Finthrive | 1 |  |  |  |  | 2025-06-23
Gaurdian | 1 |  |  |  |  | 2025-07-01
Apple | 1 |  |  |  |  | 2025-07-01
Equifax |  |  | 1 |  |  | 2025-07-03
Vandalia | 1 |  |  |  |  | 2025-07-03
Apple | 1 |  |  |  |  | 2025-07-08
Promptcare | 1 |  |  |  |  | 2025-07-10
Comcast | 1 |  |  |  |  | 2025-07-10
Icertis | 1 | 1 | 1 |  |  | 2025-07-15
Accenture FIS - Agentic/DU | 2 |  |  |  |  | 2025-07-15
Equifax | 1 |  |  |  |  | 2025-07-17
Apple | 1 |  |  | 1 |  | 2025-07-18
Cigna Agentic | 1 |  | 1 |  |  | 2025-07-29
FinThrive | 1 |  |  |  |  | 2025-07-29
Intel | 1 |  |  |  |  | 2025-08-07
Micron | 1 |  |  |  |  | 2025-08-14
Standard Insurance | 1 |  |  |  |  | 2025-08-14
Citizens Bank | 1 |  |  |  |  | 2025-08-14
Intel | 1 |  |  |  |  | 2025-08-19
Pepsi Co | 1 |  |  |  |  | 2025-08-20
Take 2 | 1 |  |  |  |  | 2025-08-20
Micron | 1 |  |  |  |  | 2025-08-21
Avista | 1 |  |  |  |  | 2025-08-25
FMC |  |  | 1 |  | 1 | 2025-08-26
Apple | 1 |  |  |  |  | 2025-09-10
Voya | 3 |  |  |  |  | 2025-09-12
Skanska | 1 |  |  |  |  | 2025-09-16
BOA | 1 |  |  |  |  | 2025-09-25
JCI - Agentic | 1 |  | 1 |  |  | 2025-10-06
CS University | 1 |  |  |  |  | 2025-10-16
Finthrive Agentic | 1 |  | 1 |  |  | 2025-10-17
Endurance Services | 1 |  |  |  |  | 2025-10-31
Denso |  |  | 1 |  |  | 2025-11-04
J&J | 1 |  | 1 |  |  | 2025-11-05
BJ's | 1 |  |  |  |  | 2025-11-13
CS University | 1 |  |  |  |  | 2025-11-14
JCI - Agentic | 1 |  | 1 |  |  | 2025-11-18
Memorial Sloan Kettering | 1 |  |  |  |  | 2025-11-18
CareSource |  |  | 1 |  |  | 2025-11-18
CareSource | 1 | 1 |  |  |  | 2025-12-24
Total | 48 | 2 | 11 | 2 | 1
Note on A8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Raghavendra
Note on A11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Raju Naik
Note on A12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Purushotham Bathula
Note on A13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Raghavendra
Note on A14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Amaladeepan 312 Hrs only
Note on A15: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Bhabagrahi Lenka
Note on A16: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Prativa Karali
Note on A17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Vamsi Krishna
Note on A18: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: SA_ Rajat Gupta, BA - Debashish, DU Dev - Ranjit Udaykumar
Note on A19: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: DU Dev - Amit Joshi, Vasantha R
Note on A20: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Dev - Anand Karn
Note on A21: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Dev - Kalki Suresh Kuma, PM - Amit Kumar
Note on A22: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Dev - Pranet, SA - Vasanth
Note on A23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: DU Dev - Ritesh Burman
Note on A24: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Santhosh Arjun
Note on A25: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Chetan Dawan
Note on A26: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: George Ken
Note on A27: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Syed Abdahir
Note on A28: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Ritesh Burman
Note on A29: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Vasantha R
Note on A30: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Raju Naik
Note on A31: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Dev - Chetan Dawan
Note on A32: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Dev - Vasanth S
Note on A33: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: SA - Saranya , Infra - Arjun
Note on A34: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Navas Hamsa
Note on A35: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Developers - Anshuman, Mina Mundhe, Dharunya
Note on A36: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Sanjana M
Note on A37: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Shubam Jhadav
Note on A38: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: SA - Vasanth Sankaran, Sr. Dev - Abishek Singh
Note on A39: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Dev - Sarita Shukla
Note on A40: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: DU Dev - Nikita Pai, SA - Raghav
Note on A41: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Dev - Hitesh Kumar
Note on A42: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: SA - LIri
Note on A43: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: SA - k. Veerapandiyan Dev - Vinod Badgujar
Note on A44: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Agentic Dev - Shlok Singh
Note on A45: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Dev - Sachdeep Singh
Note on A46: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: SA - Chaman, Dev - Shivanugowda
Note on A47: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Dev - Karthik Deshpande
Note on A48: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: SA - Sagi Shailendra
Note on A49: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: BA - Rijan Gaha, Dev - Varun Bharadwaj

## Utilization
CW | WE_20 Sep | WE_27 Sep | WE_04 Oct | WE_11 Oct
FDS% | 80% | 81% | 75% | 82%
Non-FDS% | 20% | 19% | 25% | 18%
FTE | WE_20 Sep | WE_27 Sep | WE_04 Oct | WE_11 Oct
FDS% | 68% | 71% | 38% | 64%
Non-FDS% | 32% | 29% | 62% | 36%
CW | Oct '24 | Nov '24 | Dec '24
FDS% | 79% | 87% | 76%
Non-FDS% | 21% | 13% | 24%
FTE | Oct '24 | Nov '24 | Dec '24
FDS% | 70% | 72% | 71%
Non-FDS% | 30% | 28% | 29%

## Summary Dashboard
PS India GDH - AMER Delivery Overview
Total Active Projects |  | On Tracl | At Risk | Delayed | On Track | 51 | 77.27%
[5 empty] | Delayed | 7 | 10.61%
66 |  | 51 | 0 | 7 | On Hold | 4 | 6.061%
[5 empty] | Yet to Start | 4 | 6.061%
[5 empty] | Total | 66 | 100%
Completed All Time |  | Blocked | On Hold | Yet to Start
|  | 0 | 4 | 4
[5 empty] | Core | 28 | 42.42%
[5 empty] | Growth | 38 | 57.58%
[5 empty] | Total | 66 | 100%
[8 empty] | Area | Project Name | Service Type | Contract Value | ContractType | ARR | Project Stage | Project Type | Project Health | Objective of PS | Remaining Budget
[8 empty] | AMER HLS | HCA – Information Technol-Hybrid-Service Credit Prepaid-004732 | IXP/GenAI/Comms Mining | 2500000 | Service Credit | 16598514.69 | Development | IXP/GenAI/Comms Mining | Green | RPA, DU, IXP based automation implementations
[8 empty] | AMER HLS | CIGNA-Hybrid-Service Credit Prepaid-100% Discounted-PR-010280 | Agentic | 2500000 | Service Credit | 15220001.17 | Development | Agentic | Amber | Agentic implementation
[8 empty] | AMER FINS | Wells Fargo (Global)-Hybrid-Service Credit-100% Disc- Prepaid-009742 | Test Cloud | 1600000 | T&M | 13500004.18 | Live | Test Cloud | Green | On Prem to dedicated Saas migration
[8 empty] | AMER GSI | Deloitte Global Services-Hybrid-Service Credit Prepaid-PR-008208 | Core | 1470000 | Service Credit | 13000000 | Development | Core | Green | RPA, DU, IXP based automation implementations
[8 empty] | AMER FINS | Citizens Bank National A-Fixed Price-100% disc.-Service Credit Prepaid-008086 | Core | 1300000 | Fixed Fee | 4270000.03 | Development | Core | Green | RPA, DU, IXP based automation implementations
[5 empty] | Agentic | 10 | 26.32% | AMER SUMMIT | Google Inc.-Fixed Price-Prepaid-100% Discounted-009073 | Test Cloud | 5402500 | Fixed Fee | 4087790.39 | Development | Test Cloud | Red | Test suite implementation for application testing
[5 empty] | IXP / Comms Mining | 21 | 55.26% | AMER FINS | Liberty Mutual Insurance-Hybrid-Service Credit Prepaid-100% Discounted-005449 | Apps, API | 7000000 | T&M | 3506777.17 | UAT | Apps, API | Green | RPA, DU, Test Suite and Apps implementations
[5 empty] | Test Cloud | 5 | 13.16% | AMER SUMMIT | ExxonMobil (Global)-Hybrid-Service Credit Prepaid-100%Disc-011039 | Test Cloud | 400000 | Service Credit | 3154429.84 | Development | Test Cloud | Green | Test suite implementation for application testing
[5 empty] | Apps, API | 1 | 2.632% | AMER SUMMIT | Apple-Fixed Price-Service Credit Prepaid 100% Discounted-PR-010148 | Core | 2300000 | Service Credit | 2753232.76 | Development | Core | Green | RPA automation implementation and Technical advisory services
[5 empty] | Training | 1 | 2.632% | AMER Commercial | Icertis Inc.-Hybrid-Service Credit Prepaid-PR-009786 | IXP/GenAI/Comms Mining | 1000000 | Service Credit | 2000000 | Development | XP/GenAI/Comms Mining | Green | RPA, DU, IXP based automation implementations
[5 empty] | Total | 38 | 100%
[8 empty] | Area | Project Name | Project Type | Contract Value | Contract Type | ARR | Reason for Hold | Mitigation
[8 empty] | AMER GSI | Deloitte Consulting LLP-Hybrid-Service Credit Prepaid- 100% Discounted-009807 | Test Suite | 622000 | Fixed Fee |  | Enabling infra access | Moved to Exxon Mobil Project
[8 empty] | AMER SUMMIT | Amazon - Global Freight P-Fixed Price-Prepaid-009950 | Core | 74994 | Fixed Fee |  | Enabling infra access | None - as customer has no clue on further steps
[8 empty] | AMER HLS | Tenet Business Services C-Time and Materials-Prepaid-PR-009919 | Core | 21700 | Fixed Fee | 710768 | Tenet internal re-org | Awaiting AE to confirm
[8 empty] | AMER Commercial | Lydonia Te-Falvey Insuran-Time and Materials-POD-010347 | Core | 3993.75 | T&M | 70791.6 | No forecast of work | Customer confirmed to close the Project
[8 empty] | Area | Project Name | Deal Value | Project Type | SOW Type | Contract Type | Status | RAG Status | Delay reasons | Mitigation Plan
[8 empty] | AMER SUMMIT | Google Inc.-Fixed Price-Prepaid-100% Discounted-009073 | 5402500 | Test Cloud | Delivery | Fixed Fee | In Progress | Delayed | Customer Delays, Project delayed : Infra, Onboarding process and Security Review | Being internally discussed within PS leadership on way forward
[8 empty] | AMER HLS | FinThrive Revenue Systems-Hybrid-Service Credit Prepaid-100% Discounte-PR-009904 | 500000 | Agentic | Delivery | Service Credit | In Progress | Delayed | PM Anthony Garcia, now Aditya communicated on 09/26 on customers decision to put project on HOLD | Awaiting customers response to resume the project
[8 empty] | AMER SUMMIT | Johnson Controls Inc.-Fixed Price-Postpaid-010614 | 185559 | Agentic | Delivery | Service Credit | In Progress | Delayed | Continous scope creps delayed the overall delivery | Scheduled discussion 02/27 with stakeholders to agree upon the scope freeze
[8 empty] | AMER FINS | Verdad Informatica de Cos-Fixed Price-POD-010309 | 166921 | Agentic | Delivery | Service Credit | In Progress | Delayed | Delayed due to Scope creeps and availability of billable efforts | Escalated with Sr. leadership to freeze the scope for every release to avoid delays and budget spilover
[8 empty] | AMER SUMMIT | Skanska USA- Fixed Price-Prepaid- 100% DISC-010503 | 152800 | Core | Delivery | Fixed Fee | In Progress | Delayed | Delayed due to license and infra readiness, SME availability to complete testing | Scheduled discussion 02/27with stakeholders to agree upon the UAT and go-live completion targets
[8 empty] | AMER Public Sector | Carahsoft-Columbus State-Fixed Price-POD-PR-010537 | 91007 | XP/GenAI/Comms Mining | Delivery | Fixed Fee | In Progress | Delayed | Delivery was on hold for a month - challenge in enabling app access | Dev onboarding in progress, customer being followed up for enabling access, no ETA
[8 empty] | AMER HLS | J&J World HQ-NJ-Time and Materials-Prepaid-010644 | 42628 | Core | Delivery | Service Credit | In Progress | Delayed | UAT Delayed due to Outlook configurations | Meetings cheduled with stakeholders 02/27 on implementation of webmail as alternate soln for outlook per customer ask

## Updated Pivot
Project by Delivery Region |  |  | Projects by Contract Type
Row Labels | Count of Project Name |  | Row Labels | Count of Project Name
India | 37 | 56.06% | Fixed Fee | 21 | 31.82%
India/US | 29 | 43.94% | Service Credit | 20 | 30.3%
Grand Total | 66 | 100% | T&M | 25 | 37.88%
|  |  | Grand Total | 66 | 100%
Project by Type
Row Labels | Count of Project Name | %
Delivery | 38 | 57.58%
MS | 7 | 10.61%
Staff Aug | 21 | 31.82%
Grand Total | 66 | 100%
Row Labels | Count of Project Name | % | Row Labels | Count of Project Name |  | Service/Product Type | Count | Percentage
In Progress | 57 | 86.36% | Core | 28 |  | Growth | 38 | 57.58%
On HOLD | 5 | 7.576% | Core | 28 |  | Agentic | 9 | 23.68%
Yet to Start | 4 | 6.061% | Growth | 38 |  | Apps, API | 1 | 2.632%
Grand Total | 66 | 100% | Agentic | 10 |  | XP/GenAI/Comms Mining | 22 | 57.89%
|  |  | Apps, API | 1 |  | Test Cloud | 5 | 13.16%
|  |  | Training | 1 |  | Training | 1 | 2.632%
|  |  | XP/GenAI/Comms Mining | 21 |  | Core RPA | 28 | 42.42%
|  |  | Test Cloud | 5 |  | Grand Total | 66 | 100%
|  |  | Grand Total | 66
Area | Count of Projects |  | Count of Project Name | Column Labels
AMER SUMMIT | 24 | Joseph Yoon | Area | Non-Strikezone | Strikezone | Grand Total
AMER FINS | 16 | Chris Heller | AMER FINS | 7 | 9 | 16
AMER HLS | 14 | Joseph Yoon | AMER Commercial | 6 | 1 | 7
AMER Commercial | 7 | Chris Heller | AMER Public Sector |  | 1 | 1
AMER GSI | 2 | Joseph Yoon | Grand Total | 13 | 11 | 24
Internal | 2 | Chris Heller
AMER Public Sector | 1
Grand Total | 66
Chris Heller
Area | US Lead
AMER SUMMIT | Joseph Yoon
AMER FINS | Andrew Clemmensen
AMER HLS | Andrew Clemmensen
AMER Commercial | Joseph Yoon
AMER GSI
AMER Public Sector | Chris Heller

## AMER Project Details FY 26
Sl. No | Project Delivery | Project ID | Area | Account | Project Name | Account Exec | GTM | Customer SPOC | Backlog [Delivered Value] | Deal Value | Growth/Core | SZ/NSZ | Project Type | Delivery Region | SOW Type | Contract Type | Status | Resources FTE | Resources CW | RAG Status | Issues | Comments | SOW Signed on | Project End date | Project Manager | PM Geo
1 | Intl - AMER | PR-005449 | AMER FINS | Liberty Mutual Insurance | Liberty Mutual Insurance-Hybrid-Service Credit Prepaid-100% Discounted-005449 | Andrew Warren |  | george.kochiii@libertymutual.com | 90230 | 7000000 | Growth | Strikezone | Apps, API | India | Staff Aug | T&M | In Progress |  | 1 | Green | No | Apps and API's are extensively used in the automation, 1 developer from PS India is supporting with the development, frequent changes from customer are being incorporated and moving ahead. | 2023-01-29 | 2026-03-20 | Thiyag | India
2 | Test - AMER | PR-009073 | AMER SUMMIT | Google Inc | Google Inc.-Fixed Price-Prepaid-100% Discounted-009073 | Tylor Basas | Nolyn Croy |  | 4552146.5 | 5402500 | Growth | Strikezone | Test Cloud | India/US | Delivery | Fixed Fee | In Progress | 3 |  | Delayed | Yes | Customer Delays, Project delayed : Infra, Onboarding process and Security Review | 2024-07-31 | 2026-07-30 | Alain Herrera | US
3 | Intl - AMER | PR-0101280 | AMER HLS | CIGNA | CIGNA-Hybrid-Service Credit Prepaid-100% Discounted-PR-010280 | Ryan Poole |  |  | #N/A | 2500000 | Growth | Strikezone | Agentic | India/US | Delivery | Service Credit | On HOLD |  |  | Green | No | Project on Hold due to technical feasibility, Product team has responded not feasible to automate through Agentic | 2025-07-01 | 2027-06-30 | Aditya Kottapalli | US
4 | Intl - AMER | PR-004732 | AMER HLS | HCA Information Technology & Services, Inc. | HCA – Information Technol-Hybrid-Service Credit Prepaid-004732 | Susan Belovich |  | Daniel Alexander daniel.alexander@hcahealthcare.com |  | 2500000 | Growth | Strikezone | XP/GenAI/Comms Mining | India/US | Delivery | Service Credit | In Progress |  |  | Green | No | DU/IXP implementation, Dev onboarding in progress | 2022-10-31 | 2026-04-30 | Whitney Holmes | US
5 | Intl - AMER | PR-010148 | AMER SUMMIT | Apple | Apple-Fixed Price-Service Credit Prepaid 100% Discounted-PR-010148 | Ryan Edmundowicz |  | Bosco D'Silva bdsilva@apple.com | 1782730 | 2300000 | Core | Strikezone | Core | India/US | Delivery | Service Credit | In Progress | 2 | 5 | Green | No | Implementation of Core RPA use cases, SA and Developers from PS India - BA and PM from PS US | 2025-05-27 | 2027-05-26 | Alain Herrera | US
6 | Test - AMER | PR-009742 | AMER FINS | Wells Fargo (Global) | Wells Fargo (Global)-Hybrid-Service Credit-100% Disc- Prepaid-009742 |  | Nolyn Croy |  | 589280 | 1600000 | Growth | Non-Strikezone | Test Cloud | India | Staff Aug | T&M | In Progress | 12 | 14 | Green | No | Migration Completed | 2025-04-01 | 2026-09-30 | Thiyag | India
7 | Intl - AMER | PR-008208 | AMER GSI | Deloitte Global Services LLP | Deloitte Global Services-Hybrid-Service Credit Prepaid-PR-008208 | Erika Laughlin |  | Ragu Gurumurthy rgurumurthy@deloitte.com | 924189 | 1470000 | Core | Strikezone | Core | India | Delivery | Service Credit | In Progress | 2 | 4 | Green | No | Delivery of Assignment Generation and Governance and Compliance use cases Completed Phase I & II , CR Phase 1 completed and Phase 2 in progress | 2023-10-30 | 2026-10-30 | Kamal | India
8 | Intl - AMER | PR-008086 | AMER FINS | Citizens Bank, National Association | Citizens Bank National A-Fixed Price-100% disc.-Service Credit Prepaid-008086 | Aaron Greenblatt |  | Matthew Lavoie matthew.d.lavoie@citizensbank | 182650 | 1300000 | Core | Non-Strikezone | Core | India | Staff Aug | Fixed Fee | In Progress | 1 | 6 | Green | No | BP to UiPath Migrations, new impelmentations, functionality enhancements of BOT's already deployed in Prod | 2023-11-23 | 2026-11-23 | Thiyag | India
9 | Intl - AMER | PR-009786 | AMER Commercial | Icertis, Inc. | Icertis Inc.-Hybrid-Service Credit Prepaid-PR-009786 | Lawrence Dixon |  | Todd Smith todd.smith@icertis.com | 989300 | 1000000 | Growth | Non-Strikezone | XP/GenAI/Comms Mining | India | Delivery | Service Credit | In Progress | 0.5 | 2 | Green | No | Implementation of DU Use case and explorig ROI of 10 use cases accorss Finance and HR domains - All Indi Staffig | 2025-01-31 | 2027-01-30 | Kamal | India
10 | Test - AMER | PR-009807 | AMER GSI | Deloitte Consulting, LLP | Deloitte Consulting LLP-Hybrid-Service Credit Prepaid- 100% Discounted-009807 | Erika Laughlin | Nolyn Croy |  | 610555.2 | 622000 | Growth | Strikezone | Test Cloud | India | Delivery | Fixed Fee | ON HOLD | 3 |  | Green | No | delivery shifted to Exxon Mobil PR-011039 | 2025-05-15 | 2026-05-14 | Joseph Yoon | US
11 | Intl - AMER | PR-010972 | AMER HLS | Ascension Health Alliance | Ascension Health Alliance-Hybrid-Service Credit Prepaid-100%Disc-010972 | Dannie Aschenbrener |  | Gagan Singh, gagan.singh@ascension.org |  | 550000 | Growth | Strikezone | XP/GenAI/Comms Mining | India/US | Delivery | Service Credit | In Progress |  |  | Green | No |  | 2025-11-26 | 2026-11-25 | Kristen Casterline | US
12 | Intl - AMER | PR-009904 | AMER HLS | FinThrive Revenue Systems, LLC | FinThrive Revenue Systems-Hybrid-Service Credit Prepaid-100% Discounte-PR-009904 | Robert Lord | Lindsay Galvin | Michael Waluk michael.waluk@finthrive.com | 58333.45 | 500000 | Growth | Strikezone | Agentic | India/US | Delivery | Service Credit | In Progress |  |  | Delayed | No | PM Anthony Garcia, now Aditya communicated on 09/26 on customers decision to put project on HOLD | 2025-01-31 | 2028-01-30 | Aditya Kottapalli | US
13 | Intl - AMER | PR-010485 | AMER FINS | Voya Services Company | Voya Services Company-Time and Materials-POD 010485 | Angela Li |  | Guy Conille guy.conille@uipath.com | 610000 | 457500 | Growth | Strikezone | Agentic | India/US | Delivery | Service Credit | In Progress | 2 | 1 | Green | No | Deveopment in Progress | 2025-08-19 | 2027-08-18 | Guy Conille | US
14 | Intl - AMER | PR-011316 | AMER FINS | Hub International | Hub International-Fixed Price-Postpaid-011316 | John Pellettiere | Nolyn Croy | Seth McCallister seth.mccallister@hubinternational.com |  | 420000 | Core | Non-Strikezone | Core | India | MS | Fixed Fee | In Progress |  |  | Green | No | Managed Services delivered by WBZ | 2026-02-09 | 2027-03-08 | Sandip | India
15 | Intl - AMER | PR-011298 | AMER HLS | Access Telecare, LLC | Access Telecare LLC-Hybrid-Postpaid-011298 | Colby LaCouture |  | Andy Garlington Email bounced. Update the email address and try again.andy.garlington@accesstelecare.com |  | 410400 | Growth | Strikezone | Agentic | India/US | Delivery | Fixed Fee | Yet to Start |  |  | Green | No | Agentic implementation in MAC yet to start and to be Staffed | 2026-02-02 | 2028-02-01 | Kristen Casterline | US
16 | Test - AMER | PR-011039 | AMER SUMMIT | ExxonMobil (Global) | ExxonMobil (Global)-Hybrid-Service Credit Prepaid-100%Disc-011039 | Sam Ghosh | Lisa Goodman | Saysha Reyes Chica |  | 400000 | Growth | Strikezone | Test Cloud | India | Delivery | Service Credit | In Progress | 0.5 | 2 | Green | No | Test Suite implementation | 2025-12-02 | 2026-12-21 | Hitesh Kumar | India
17 | Intl - AMER | PR-010592 | AMER FINS | Western Alliance Bank | Western Alliance Bank-Time and Materials-Prepaid-100%Disc-010592 | Carl Zauner | Nolyn Croy |  | 355500.56 | 359600 | Growth | Strikezone | Agentic | India/US | Delivery | Service Credit | In Progress |  | 1 | Green | No | Agenic Use case - 2 developers requested from PS India likely to start in last week of Oct 2025, per PS US PM | 2025-09-24 | 2027-09-23 | Xiwen Shui | US
18 | Intl - AMER | PR-010989 | AMER SUMMIT | Intel Corporation | Intel Corporation-Time and Materials-Postpaid-010989 | Zach Venard |  | Shah, Siddharth siddharth.shah@intel.com |  | 300000 | Growth | Non-Strikezone | XP/GenAI/Comms Mining | India | Staff Aug | T&M | In Progress |  |  | Green | No | Implementation of DU, ML and Core RPA use cases from PS India, being renewed YoY for the past 3 years | 2025-12-11 | 2027-12-10 | Kamal | India
19 | Test - AMER | PR-010169 | AMER FINS | Voya Services Company | Voya Services Company-Hybrid-Prepaid 100% Discounted-010169 | Aaron Greenblatt | Lisa Goodman | Pratik Kothari | 252398.965 | 299975 | Growth | Strikezone | Training | India/US | Delivery | Fixed Fee | In Progress | 2 | 1 | Green | No |  | 2025-06-05 | 2027-06-13 | Nisha Shweta | India
20 | Intl - AMER | PR-009891 | AMER HLS | The Promptcare Companies Inc | The Promptcare Companies-Fixed Price-Prepaid-009891 | Jonathan Harrison | Spencer Miller | Phill Merrell pmerrell@promptcare.net | 231899.598 | 278029 | Growth | Strikezone | XP/GenAI/Comms Mining | India | Delivery | Fixed Fee | In Progress |  |  | Green | No | All India Staffing - DU | 2025-03-18 | 2027-03-18 | Hitesh Kumar | India
21 | Intl - AMER | PR-009890 | AMER HLS | The Promptcare Companies Inc | The Promptcare Companies-Fixed Price-100% DISC-Prepaid-009890 | Jonathan Harrison | Spencer Miller | Phill Merrell pmerrell@promptcare.net | 198977.727 | 273810 | Growth | Strikezone | XP/GenAI/Comms Mining | India | Delivery | Fixed Fee | In Progress |  |  | Green | No | All India Staffing - DU | 2025-03-18 | 2026-03-18 | Hitesh Kumar | India
22 | Intl - AMER | PR-010980 | AMER HLS | CareSource | CareSource-Time and Materials-Prepaid-010980 | Christopher Bingham |  | Pranay Jauhri pranay.jauhri@caresource.com |  | 225000 | Growth | Strikezone | XP/GenAI/Comms Mining | India/US | Delivery | T&M | In Progress | 3.5 | 0.5 | Green | No | DU/IXP implementation in progress | 2025-12-04 | 2027-04-03 | Aditya Kottapalli | US
23 | Intl - AMER | PR-009664 | AMER FINS | Alliant Credit Union | Alliant Credit Union-Time and Materials-POD-009664 | John Pellettiere | Nolyn Croy |  | 229726.8 | 196432 | Growth | Non-Strikezone | XP/GenAI/Comms Mining | India/US | Delivery | T&M | In Progress | 0.5 | 2 | Green | No | Implementation of Core RPA use cases - SA and 2 Devs from India, US PM and BA | 2025-01-24 | 2027-01-23 | Sreedhar Lakkavaram | US
24 | Intl - AMER | PR-010614 | AMER SUMMIT | Johnson Controls, Inc. | Johnson Controls Inc.-Fixed Price-Postpaid-010614 | Steven Lawrence | Spencer Miller | Navroop Kaur Bal navroop.kaur.bal@jci.com | 250755 | 185559 | Growth | Strikezone | Agentic | India/US | Delivery | Service Credit | In Progress |  |  | Delayed | No | Delays in availability of API info and app Schema | 2025-09-08 | 2026-09-30 | Charlie Hirsch | US
25 | Intl - AMER | PR-010835 | AMER SUMMIT | BJ's Wholesale Club | BJ's Wholesale Club.-Hybrid-Service Credit Prepaid-100%Disc-010835 | Dave Giannattasio |  | Monica Schwartz |  | 175000 | Growth | Strikezone | XP/GenAI/Comms Mining | India/US | Delivery | Service Credit | In Progress | 2.5 | 2 | Green | No | Almost all growth Products being explored and implemented from Test Suite, DU, Gen AI, Agentic, Comms Mining , Context Grounding etc. SA BA Dev from PS India - PM frm PS US | 2025-10-31 | 2028-10-30 | Noa Olson | US
26 | Intl - AMER | PR-010309 | AMER FINS | Equifax Inc. | Verdad Informatica de Cos-Fixed Price-POD-010309 | Kristin Collins |  |  | 140143.11 | 166921 | Growth | Strikezone | Agentic | India/US | Delivery | Service Credit | In Progress | 1 | 1 | Delayed | No | Delayed due to Scope creeps and availability of billable efforts | 2025-06-25 | 2026-07-25 | Juan Garay | US
27 | Intl - AMER | PR-011038 | AMER HLS | CAMC Health System | CAMC Health System-Fixed Price-Postpaid-011038 | Nawal Alami |  | Jeff Cox jeff.cox@vandaliahealth.org |  | 165480 | Growth | Strikezone | Agentic | India/US | Delivery | Fixed Fee | Yet to Start |  |  | Green | No | Agentic implementation yet to start and to be Staffed | 2025-12-22 | 2027-12-21 | Kristen Casterline | US
28 | Intl - AMER | PR-008662 | AMER SUMMIT | Intuit | Intuit Inc.-Time and Materials-Prepaid-PR-008662 | Tylor Basas |  | Maaly Mohamed maaly_mohamed@intuit.com | 81422 | 163900 | Core | Non-Strikezone | Core | India | Staff Aug | T&M | In Progress | 0 | 1 | Green | No | Staff Aug Project being supported for the past 3 years, YoY renewal, Core RPA use cases | 2024-03-18 | 2027-06-02 | Sandip
29 | Intl - AMER | PR-010111 | AMER SUMMIT | PACCAR Inc. | PACCAR Inc.-Time and Materials-Prepaid-100% Discounted-PR-010111 | Ryan Cousins | Spencer Miller | Abhijit.Chaporka Abhijit.Chaporkar@PACCAR.com | 100400.64 | 163200 | Core | Non-Strikezone | Core | India | MS | Fixed Fee | In Progress | 0.25 | 3.5 | Green | No | Managed Services, Post Go-live Biz Support | 2025-05-14 | 2026-05-13 | Sandip
30 | Intl - AMER | PR-010503 | AMER SUMMIT | Skanska USA | Skanska USA- Fixed Price-Prepaid- 100% DISC-010503 | Aman Alagh |  |  | 152800 | 152800 | Core | Non-Strikezone | Core | India/US | Delivery | Fixed Fee | In Progress |  | 1.5 | Delayed | No | Delayed due to API info and SME availability to complete testing | 2025-09-01 | 2026-10-21 | Charlie Hirsch | US
31 | Intl - AMER | PR-008575 | AMER FINS | Massachusetts Mutual Life Insurance Company | Massachusetts Mutual Life-100%discounted-Service Credit Prepaid-008575 | Matthew Dirubio |  | Arthur Riel ariel11@massmutual.com | 140220 | 150000 | Growth | Non-Strikezone | XP/GenAI/Comms Mining | India/US | Staff Aug | Service Credit | In Progress |  | 0.5 | Green | No | Technical support, feasibility assessment, POC's, our SA's will support and guide customers with Design and deployment initialy 1 SA with 50% was deployed, In Sep '25 added 1 fulltime SA | 2023-10-31 | 2026-10-30 | Thiyag | India
32 | Intl - AMER | PR-010219 | AMER Commercial | Avista Corporation | Avista Corporation-Fixed Price-Service Credit Prepaid-100% Discounted-PR-010219 | Zane Bushnell |  | Jason Pegg ason.pegg@avistacorp.com | 129259 | 130000 | Growth | Strikezone | Agentic | India | Delivery | Service Credit | In Progress | 1 | 1.5 | Green | No | Implementation of core RPA use case - All India Staffing, customer projects potential use case on Agentic, in Hypercare now | 2025-06-17 | 2027-06-16 | Kamal | India
34 | Intl - AMER | PR-009958 | AMER SUMMIT | Snap-On Credit LLC | Lydonia Te-Snap-On Credit-Time and Materials-POD-PR-009958 | Elliott Davis | Spencer Miller | Kevin Scannell kevin@lydonia.ai | 101890.43 | 124406 | Core | Non-Strikezone | Core | India | Staff Aug | T&M | In Progress |  |  | Green | No | Implementation of DU and Core RPA use cases, SA and Dev , being renewed for last 2 years with PS India | 2025-04-02 | 2027-04-01 | Kamal
35 | Intl - AMER | PR-010186 | AMER SUMMIT | Group 1 Automotive | Group 1 Automotive-Time and Materials-Prepaid-010186 | Lindsay Kincy |  | Al Omari aomari@group1auto.com | 127759.5 | 123750 | Core | Non-Strikezone | Core | India | Staff Aug | T&M | In Progress |  | 2 | Green | No | Staff Aug Project being renewed YoY since 2023, core RPA use cases supported by PS India staff | 2025-06-11 | 2027-06-10 | Kamal
| Intl - AMER | PR-011340 | AMER FINS |  | Hub International-Time and Materials-Postpaid-011340 |  |  |  |  | 595200 | Growth |  | XP/GenAI/Comms Mining | india | Delivery | T&M | In Progress |  |  | Green | No | Implementation of DU, ML and Core RPA use cases from PS India, being renewed YoY for the past 3 years | 2026-02-15 | 2028-02-18 | Hitesh Kumar | India
37 | Intl - AMER | PR-010216 | AMER SUMMIT | Leica Microsystems Inc. | Leica Microsystems Inc.-Time and Materials-Prepaid-PR-010216 |  |  |  | 90594.24 | 105600 | Core | Non-Strikezone | Core | India | MS | T&M | In Progress |  |  | Green | No | Managed Service Project | 2025-05-23 | 2027-05-22 | Sandip
38 | Intl - AMER | PR-010897 | AMER SUMMIT | PACCAR Inc. | PACCAR Inc.-Fixed Fee-Prepaid-010897 | Ryan Cousins | Spencer Miller | Abhijit.Chaporka Abhijit.Chaporkar@PACCAR.com |  | 102000 | Core | Non-Strikezone | Core | India | MS | Fixed Fee | In Progress |  |  | Green | No | Managed Services, Post Go-live Biz Support | 2025-11-07 | 2027-11-06 | Sandip
39 | Intl - AMER | PR-010716 | AMER Commercial | Angelo Gordon US | Lydonia Te-Angelo Gordon-Time and Materials-POD-010716 | Zach Elkinson | Spencer Miller | Michael Mullaney mmullaney@glanbia.ie |  | 101575.65 | Core | Non-Strikezone | Core | India | Staff Aug | T&M | In Progress |  |  | Green | No | Implemenattion of Core RPA use cases from PS India - All inidia Staffing, being renewed for last 3 tears with PS India | 2025-10-16 | 2028-10-31 | Kamal | India
40 | Intl - AMER | PR-010548 | AMER SUMMIT | Total Quality Logistics | Total Quality Logistics-Hybrid-Service Credit Prepaid-100%Disc-PR-010548 | Brandon Sage | Nolyn Croy |  |  | 100000 | Growth | Strikezone | XP/GenAI/Comms Mining | India | Delivery | Service Credit | In Progress | 1 | 1.75 | Green | No | Implementation of DU / IXP use cases | 2024-10-16 | 2026-10-15 | Kamal | India
41 | Intl - AMER | PR-009156 | AMER Commercial | America Fujikura Ltd | Lydonia Te-America Fujiku-Time and Materials-POD-009156 | Behrad Shahnavaz | Spencer Miller | Michael Mullaney mmullaney@glanbia.ie | 14672.3473 | 93934.77 | Growth | Non-Strikezone | XP/GenAI/Comms Mining | India | Staff Aug | T&M | In Progress | 0 | 1 | Green | No | Implementation of DU and Core RPA use cases, SA and Dev , being renewed for last 2 years with PS India | 2024-08-30 | 2026-09-02 | Kamal | India
42 | Intl - AMER | PR-010537 | AMER Public Sector | Columbus State University: GEORGIA BOARD OF REGENTS | Carahsoft-Columbus State-Fixed Price-POD-PR-010537 | Jack Persinger |  | Ted Laskaris laskaris_theodore@columbusstate.edu | 128180 | 91007 | Growth | Strikezone | XP/GenAI/Comms Mining | India/US | Delivery | Fixed Fee | In Progress |  | 1.5 | Delayed | No | Delivery was on hold for a month - challenge in enabling app access, dev fromPS india onboarding in progress | 2025-09-08 | 2026-09-07 | Charlie Hirsch | US
43 | Intl - AMER | PR-010528 | AMER FINS | Endurance Services Limited | Endurance Services Limite-Fixed Price-POD-PR-010520 | Graham Newby |  | Joseph Fox jfox@sompo-intl.com | 86818 | 86818 | Growth | Strikezone | XP/GenAI/Comms Mining | India/US | Delivery | Fixed Fee | In Progress |  | 1 | Green | No | Implementation of DU usecase | 2025-08-28 | 2027-08-27 | Harsha Srikantan | US
44 | Intl - AMER | PR-009360 | AMER SUMMIT | Comcast (Cable Communications) | Comcast (Cable Communicat-Fixed Price-Prepaid 100% Discounted-009360 | Jessica Madigan |  | Sandra Lau sandra_lau@comcast.com | 620418.249 | 82540 | Core | Strikezone | Core | India/US | Delivery | Fixed Fee | In Progress | 0.5 | 2 | Green | No | Implementation of Core RPA use cases - BA< SA and 2 Devs from India, US PM | 2024-10-31 | 2026-10-30 | Noa Olson | US
45 | Intl - AMER | PR-009439 | AMER SUMMIT | Veolia WTS Services USA | Veolia WTS USA Inc.-Fixed Price-POD-009439 | Jim Stricker | Spencer Miller | Trevor Tom trevor.tom@veolia.com | 16588.8 | 81000 | Core | Non-Strikezone | Core | India | MS | Fixed Fee | In Progress | 0.25 | 1 | Green | No | Managed Services, Post Go-live Biz Support | 2024-12-04 | 2026-12-03 | Sandip
46 | Intl - AMER | PR-010414 | AMER SUMMIT | Intuit | Intuit Inc.-Time and Materials-Prepaid - PR-010414 | Brittney Thurman |  | Jean Cote jean-henri_cote@intuit.com | 103840 | 78100 | Core | Non-Strikezone | Core | India | Staff Aug | T&M | In Progress |  |  | Green | No | Staff Aug Project being supported for the past 3 years, YoY renewal, Core RPA use cases, Agentic being explored with the help of AE, TAM and Product teams | 2025-07-31 | 2027-07-30 | Sandip
47 | Intl - AMER | PR-010307 | AMER SUMMIT | Take-Two Interactive Software, Inc. | Take-Two Interactive Soft-Time and Materials-Prepaid (PR-010307) | Aman Alagh |  | Parag Khairnar parag.khairnar@take2games.com | 84480 | 78100 | Core | Non-Strikezone | Core | India | Staff Aug | T&M | In Progress | 0 | 1 | Green | No | Staff Aug Project - YoY renewal with PS India Staffing,Since 2022, Core RPA use cases | 2025-07-01 | 2027-07-02 | Thiyag
48 | Intl - AMER | PR-009051 | AMER SUMMIT | Take-Two Interactive Software, Inc. | Take-Two Interactive Soft-Time and Materials-Prepaid (PR-010308) | Aman Alagh |  | Parag Khairnar parag.khairnar@take2games.com | 5720 | 78100 | Core | Non-Strikezone | Core | India | Staff Aug | T&M | In Progress | 0 | 1 | Green | No | Staff Aug Project - YoY renewal with PS India Staffing,Since 2022, Core RPA use cases | 2024-07-24 | 2026-07-23 | Thiyag
49 | Intl - AMER | PR-010393 | AMER SUMMIT | Take-Two Interactive Software, Inc. | Take-Two Interactive Soft-Time and Materials-Prepaid (PR-010393) | Aman Alagh |  | Parag Khairnar parag.khairnar@take2games.com | 99000 | 70290 | Core | Non-Strikezone | Core | India | Staff Aug | T&M | In Progress | 0 | 1 | Green | No | Staff Aug Project - YoY renewal with PS India Staffing,Since 2022, Core RPA use cases | 2025-07-22 | 2027-07-22 | Thiyag
50 | Intl - AMER | PR-010150 | AMER Commercial | America Fujikura Ltd | Lydonia Te-America Fujiku-Time and Materials-POD-010150 | Zach Elkinson | Spencer Miller | Kevin Scannell kevin@lydonia.ai | 86120.16 | 75544 | Growth | Non-Strikezone | XP/GenAI/Comms Mining | India | Staff Aug | T&M | In Progress |  |  | Green | No | Implementation of DU and Core RPA use cases, SA and Dev , being renewed for last 2 years with PS India | 2025-04-22 | 2027-05-21 | Kamal | India
51 | Intl - AMER | PR-009950 | AMER SUMMIT | Amazon - Global Freight Partner Program | Amazon - Global Freight P-Fixed Price-Prepaid-009950 | Mohammed Danish Majeed |  |  | 106684.6 | 74994 | Core | Strikezone | Core | India/US | Delivery | Fixed Fee | On HOLD |  |  | Green | No | Project on Hold due to challenges in enabling infra access - Complete PS Indi Staff | 2025-04-01 | 2027-03-31 | Hitesh Kumar | India
52 | Intl - AMER | PR-010545 | AMER HLS | Tenet Business Services Corporation | Tenet Business Services C-Fixed Price-Prepaid-010545 | Clinton Brown | Spencer Miller | Plott, Todd todd.plott@tenethealth.net |  | 63660 | Core | Non-Strikezone | Core | India | MS | Fixed Fee | In Progress |  |  | Green | No | Post go live Managed Services Support | 2025-09-11 | 2027-09-10 | Sandip
53 | Intl - AMER | PR-010227 | AMER SUMMIT | Snap-On Credit LLC | Lydonia Te-Snap-On Credit-Time and Materials-POD-PR-010227 | Elliott Davis | Spencer Miller | Kevin Scannell kevin@lydonia.ai | 60945.5 | 54670 | core | Non-Strikezone | Core | India | Staff Aug | T&M | In Progress |  |  | Green | No | Implementation of DU and Core RPA use cases, SA and Dev , being renewed for last 2 years with PS India | 2025-06-24 | 2027-06-23 | Kamal
54 | Intl - AMER | PR-010757 | AMER HLS | Memorial Sloan Kettering Cancer Center | Memorial Sloan Kettering-Time and Materials-Prepaid-PR-010757 |  |  |  |  | 53400 | Growth | Strikezone | XP/GenAI/Comms Mining | India/US | Delivery | T&M | In Progress |  | 1 | Green | No | Implementation of DU / IXP use cases - We're using Modern DU for document splitting and IXP for extracting patient demographics information.- PAS0002_DocumentClassificationAndSplitting | 2025-10-27 | 2027-10-28 | Kristen Casterline | US
55 | Intl - AMER | PR-010590 | AMER FINS | Bank of America (Global) | Bank of America (Global)-Time and Materials-Prepaid-010590 | Andrew Warren |  | Nye Allen nye.allen@bofa.com | 52800 | 52800 | Core | Non-Strikezone | Core | India | Staff Aug | T&M | Yet to Start |  |  | Green | No | New contract signed late Sep '25, 1 dev to be onbaorded, BGV in progress, This accountis being renewed with PS India for last 3 years | 2025-09-24 | 2026-09-23 | Thiyag | India
56 | Intl - AMER | PR-010644 | AMER HLS | J&J World HQ-NJ | J&J World HQ-NJ-Time and Materials-Prepaid-010644 | Kostas Kouiroukidis |  | Venkatesan Jayaraman vjayara2@its.jnj.com | 60040 | 42628 | Core | Non-Strikezone | Core | India/US | Delivery | Service Credit | In Progress |  |  | Delayed | No | UAT Delayed due to Outlook configurations | 2025-09-18 | 2027-09-17 | Sreedhar Lakkavaram | US
57 | Intl - AMER | PR-008300 | AMER FINS | JP Morgan Chase (Global) | JP Morgan Chase(Global-Fixed Price-Service Credit Prepaid-100% Discounted-008300 | Aaron Greenblatt |  | shefali.shah@jpmchase.com | 123478.4 | 35345 | Growth | Strikezone | XP/GenAI/Comms Mining | India/US | Delivery | Service Credit | In Progress | 0.25 | 2 | Green | No | PS India staffs engaged with JPMC Platforms team in fulfilling the automation requirements coming in from intrnal BU's, includes Core RPA, DU, Agentic, ON Preom to cloud migration and Infra support, needs close coordination with TAM, Product and JPMMC Platforms | 2023-11-28 | 2026-11-27 | Kristen Casterline | US
58 | Intl - AMER | PR-011265 | Internal | Accenture India | Accenture India-Time and Materials-Prepaid-100%Disc-011265 | Girish Kumar J |  |  |  | 34698.2 | Growth | Strikezone | XP/GenAI/Comms Mining | India | Staff Aug | T&M | In Progress |  | 1 | Green | No |  | 2026-01-27 | 2027-01-26 | Thiyag
59 | Intl - AMER | PR-010064 | AMER Commercial | Edgewell Personal Care Brands, LLC | Edgewell Personal Care Br-Fixed Price-Service Credit Prepaid-100% disc_PR-010064 | Timothy Hulbert |  | Brian Mazdra brian.mazdra@edgewell.com | 25000 | 25000 | Core | Non-Strikezone | Core | India | Delivery | Service Credit | Yet to Start |  |  | Green | No | identified their top 3 scripts from "Winshuttle" migrate to UiPath low complex - Complete PS India Staffing required - NO update from customer for Kick off | 2025-04-30 | 2026-04-29
60 | Test - AMER | PR-010535 | AMER FINS | Guardian Life Insurance Company of America Inc | Guardian Life Insurance C-Time and Materials-Prepaid-010535 | Ryan Garnett | Lisa Goodman |  | 21840 | 21840 | Growth | Non-Strikezone | Test Cloud | India | Delivery | Service Credit | In Progress | 2 |  | Green |  |  | 2025-08-19 | 2027-08-18 | Vinoth Krishnan | India
61 | Intl - AMER | PR-009919 | AMER HLS | Tenet Business Services Corporation | Tenet Business Services C-Time and Materials-Prepaid-PR-009919 | Clinton Brown | Spencer Miller | Plott, Todd todd.plott@tenethealth.net | 21700 | 21700 | Core | Non-Strikezone | Core | India | MS | Fixed Fee | On HOLD | 0.25 | 3.5 | Green | No |  | 2025-03-26 | 2027-03-25 | Sandip
62 | Intl - AMER | PR-010396 | AMER SUMMIT | DENSO International America, Inc. | DENSO International Ameri-Time and Materials-Prepaid-010396 | Chris Leblanc |  | Jonathan Tylutki jonathan.tylutki@na.denso.com | 15000 | 15000 | Core | Strikezone | Core | India | Staff Aug | T&M | In Progress |  |  | Green | No | Technical Advisory services | 2025-07-30 | 2027-07-29 | Sandip
63 | Intl - AMER | PR-010394 | AMER SUMMIT | DENSO International America, Inc. | DENSO International Ameri-Time and Materials-Prepaid-010394 | Chris Leblanc |  | Jonathan Tylutki jonathan.tylutki@na.denso.com | 6000 | 6000 | Core | Strikezone | Core | India | Staff Aug | T&M | In Progress |  |  | Green | No | Technical Advisory services | 2025-07-30 | 2027-07-29 | Sandip
64 | Intl - AMER | PR-011233 | AMER HLS | IntegriChain Inc | IntegriChain Inc-Fixed Fee-Postpaid-011233 | William Robinson | Lindsay Galvin |  |  | 5000 | Growth | Strikezone | Agentic | India | Delivery | Fixed Fee | In Progress |  | 1.5 | Green | No | Pilot implementaion of Core RPA and Agentic Use case | 2026-01-29 | 2028-01-28 | Thiyag | India
65 | Intl - AMER | PR-010347 | AMER Commercial | Falvey Insurance Group | Lydonia Te-Falvey Insuran-Time and Materials-POD-010347 | Zach Elkinson | Spencer Miller | Michael Mullaney mmullaney@glanbia.ie | 5085 | 3993.75 | Core | Non-Strikezone | Core | India | Staff Aug | T&M | On HOLD |  |  | Green | No | SA support from PS India for their core RPA use case design, development and deployment, initialy 76 hrs contracted, renewed for 96 additional hours - ON Hold due to no forecast of work | 2025-07-22 | 2027-07-21 | Kamal | India
66 | Intl - AMER | PR-010925 | Internal | UiPath Inc | PSSD-1137- Internal Cross Charge - Automations for Internal ProServe-010925 |  |  |  |  | 0 | Growth | Strikezone | XP/GenAI/Comms Mining | India/US | Delivery | Fixed Fee | In Progress | 1 |  | Green | No | PS is building internal automation onPO, MCF, invoice approvals to support subcons, vendors and partner passthrough | 2025-11-25 | 2026-11-24 | Bruno Costa | US
750
Note on F12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: DU/IXP
Note on F28: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Agentic
Note on K29: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: CR to add 200 hrs approved on 29 April 2025
Note on G31: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: New York
Note on G47: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: New York

## Project Details includes Closed
Sl. No | Project Name | Deal Value | Growth/Core | Project Type | Delivery Region | SOW Type | Contract Type | Status | Resources FTE | Resources CW | RAG Status | Issues | Closed Date | SOW Signed on | Project End date
59 | Bank of New York Mellon-Hybrid-SC Prepaid-100% discounted-3 year-PR-004868 | 1600000 | Core RPA | Non-Strikezone | India | Staff Aug | Service Credit | Closed | Core | Strikezone | Green | No | 2025-10-30 | 2023-03-31 | 2026-03-30
16 | Hub International-Fixed Price-Prepaid-PR-005338 | 1021714 | Growth | Strikezone | India | MS | Fixed Fee | Closed | Closed | 3 | Green | No | 2026-02-09 | 2023-01-31 | 2026-02-09 | Sandip
47 | Homeserve USA-Fixed Price-Prepaid-009745 | 537150 | Core RPA | Non-Strikezone | India/US | Delivery | Fixed Fee | Closed | Core | Non-Strikezone | Green | No | 2025-09-10 | 2025-01-30 | 2027-01-30
60 | CAMC Health System-Hybrid-POD-009689 | 358527 | Core RPA | Non-Strikezone | India/US | Delivery | Fixed Fee | Closed |  |  | Green | No | 2025-11-15 | 2025-01-28 | 2027-01-29
61 | Tokyo Electron U.S. Holdi-Hybrid-Prepaid-008051 | 358527 | Core RPA | Non-Strikezone | India/US | Delivery | Delivery | Closed | Fixed Fee | Closed | Green | No | 2025-11-20 | 2024-03-26 | 2026-03-28
43 | Intuit Inc.-Time and Materials-Prepaid-100% Discounted-009564 | 325080 | Core | Core RPA | India/US | Staff Aug | T&M | Closed |  |  | Green | No | 2025-07-31 | 2025-01-03 | 2025-07-31
33 | Fresenius Medical Care Ho-Hybrid-Service Credit Prepaid-100% discounted-007929 | 319550 | Competitive Migration | BP to UiPath | India/US | Delivery | Service Credit | Closed | 0.25 | 4.25 | Green | No | 2025-06-16 | 2023-08-30 | 2025-08-30
31 | Ingram Mic-Vertiv Energy-Fixed Price-Prepaid-008184 | 289346 | Growth | Process Mining | India | Delivery | Fixed Fee | Closed |  |  | Green | No | 2024-03-02 | 2023-10-30 | 2024-05-17
28 | Intel Corporation-Time and Materials-POD-009522 | 240000 | DU/Gen AI | Strikezone | India | Staff Aug | T&M | Closed | In Progress |  | Green | No | 2025-12-15 | 2024-12-16 | 2026-12-15
10 | Tenet Health-Fixed Price-Partial-Prepaid-007914 | 225170 | Growth | Gen AI/DU/IDP | India/US | Delivery | Fixed Fee | On Hold | 1 | 1 | Green | No | 2025-07-17 |  | 2025-09-24
9 | RWJBH Corporate Services-Fixed Price-Partial Prepaid-008541 | 205480 | Growth | Gen AI/DU/IDP | India/US | Delivery | Fixed Fee | Closed | 1 | 0 | Green | No | 2025-02-21 |  | 2025-01-29
28 | Lydonia Te-Snap-On Credit-Time and Materials-POD-009050 | 205480 | Growth | Gen AI/DU/IDP | India | Delivery | T&M | Closed | 1 | 0 | Green | No | 2025-05-10 | 2024-06-27 | 2026-07-29
49 | PepsiCo Inc-Service Credit-100% Discounted-009972 | 200000 | Platform Migration | Strikezone | India | Staff Aug | Service Credit | Closed | In Progress | 200000 | Green | No | 2025-12-15 | 2025-04-08 | 2026-04-08
49 | Amazon-Business 2 Busi-Fixed Price-POD-008831 | 190855 | Core | Non-Strikezone | India/US | Delivery | Fixed Fee | Closed |  |  | Green | No | 2025-09-30 | 2024-05-10 | 2025-09-30
8 | Prudential USA-Time and Materials-Prepaid-006219 | 177200 | Growth | Gen AI/DU/IDP | India | Staff Aug | Fixed Fee | Closed | 0.5 | 2 | Green | No | 2025-07-17 |  | 2025-06-27
4 | BJ's Wholesale Club-Hybrid-100% discounted-Service Credit Prepaid-PR-005394 | 175000 | Growth | Strikezone | India/US | Delivery | Service Credit | Closed | 2.5 | 2 | Green | No | 2026-01-26 | 2023-01-27 | 2026-04-26
53 | PACCAR Inc.-Fixed Price-Prepaid-009306 | 162000 | Core | Non-Strikezone | India | MS | Fixed Fee | Closed | In Progress |  | Green | No | 2025-10-25 | 2024-10-22 | 2025-10-21
23 | Bank of America (Global)-Time and Materials-POD-007882 | 138250 | Platform Migration | Infra & Platform Migration | India | Staff Aug | T&M | To Be Closed |  |  | Green | No | Project status be makred as Closed in SFDC |  | 2024-08-30
38 | BetterUp Inc-Hybrid-Service Credit Prepaid-004953 | 136000 | Growth | Gen AI/DU/IDP | India | MS | Fixed Fee | Closed | 0 | 1.25 | Green | No | 2025-07-18 | 2022-10-31 | 2025-07-31
6 | PACCAR Inc-Fixed Price-Prepaid-008152 | 129365 | Growth | Gen AI/DU/IDP | India | MS | Fixed Fee | Closed |  |  | Green | No |  |  | 2024-10-30
24 | TMHCC-Fixed Price-Prepaid-009596 | 126152 | Growth | Gen AI/DU/IDP | India/US/Latam | Staff Aug | T&M | On Hold |  |  | Green | No | Project ON HOLD - Noa Olson
27 | Group 1 Automotive-Time and Materials-POD-008091 | 123750 | Growth | Gen AI/DU/IDP | India | Staff Aug | T&M | Closed | 0 | 2 | Green | No | 2024-08-31 | 2023-10-12 | 2024-09-18
41 | Group 1 Automotive-Time and Materials-POD-008966 | 123750 | Growth | Gen AI/DU/IDP | India | Staff Aug | T&M | Closed |  |  | Green | No | 2025-07-08 | 2024-07-11 | 2025-07-08
36 | Vialto Partners-Hybrid-Service Credit Prepaid-100% Discounted-006378 | 115500 | Core | Core RPA | India/US | Staff Aug | Service Credit | Closed | 1 | 0 | Green | No | 2025-07-19 | 2023-07-20 | 2025-07-19
50 | Hub International-Time and Materials-POD-PR-009736 | 115200 | Growth | Strikezone | India | Staff Aug | T&M | Closed | Closed | Green | Green | No | 2025-09-24 | 2025-01-31 | 2025-09-24
19 | Lydonia Te-Snap-On Credit-Time and Materials-POD-008197 | 113322 | Core | Core RPA | India | Staff Aug | T&M | Closed | 0.75 | 1 | Green | No | 2025-07-17 |  | 2025-01-02
32 | Carahsoft-New York Power-Fixed-POD-005090 | 108325 | Core | Core RPA | India/US | Delivery | Fixed Fee | Closed | 1.5 | 0 | Green | No | 2025-05-30 | 2023-05-26 | 2025-05-30
45 | Lydonia Te-Angelo Gordon-T&M-POD-008729 | 107575.76 | Core | Core RPA | India | Staff Aug | T&M | Closed | 0.25 | 1.5 | Green | No | 2025-07-17 | 2025-08-21 | 2025-08-21
16 | Bank of America (Global)-Time and Materials-Prepaid-008428 | 105600 | Core | Core RPA | India | Staff Aug | T&M | Closed | 1 | 0 | Green | No | 2025-07-17 |  | 2024-12-31
18 | Leica Microsystems Inc-Time and Materials-Prepaid-PR-006189 | 105600 | Core | Core RPA | India | MS | T&M | Closed | 0 | 1.25 | Green | No | 2025-07-17 |  | 2025-05-17
48 | Leica Microsystems Inc.-Time and Materials-Prepaid-008832 | 105600 | Core | Non-Strikezone | India | MS | T&M | Closed | In Progress |  | Green | No | 2025-08-12 | 2025-05-23 | 2025-08-12
2 | Paychex Inc-Hybrid-Service Credit Prepaid-100% discounted-005396 | 100000 | Growth | Gen AI/DU/IDP | India/US | Delivery | Service Credit | Closed | 1.5 | 1.25 | Green | No | 2025-02-27 |  | 2025-01-19
15 | Intel Corporation-Hybrid-Service Credit Prepaid-005996 | 100000 | Growth | Gen AI/DU/IDP | India | Staff Aug | Service Credit | Closed | 1 | 1 | Green | No | 2025-07-17 |  | 2025-04-26
58 | Houston Methodist Hospita-Hybrid-Prepaid-100% Discounted-009695 | 100000 | core | Strikezone | India/US | Delivery | Service Credit | Closed | In Progress |  | Green | No | 2025-10-31 | 2025-01-28 | 2026-01-27
52 | MGM Resorts International-Fixed Price-Prepaid-009499 | 99641 | Growth | Strikezone | India/US | Delivery | Fixed Fee | Closed | In Progress |  | Green | No | 2025-12-12 | 2024-12-20 | 2026-12-19
3 | Aon Service Corporation-Fixed Price-POD-PR-010442 | 99000 | Core | Non-Strikezone | India/US | Delivery | Fixed Fee | Closed |  | 1 | Green | No | 2026-01-20 | 2025-08-04 | 2027-09-09
37 | Take-Two Interactive Soft-Time and Materials-Prepaid-008666 | 91300 | Core | Core RPA | India | Staff Aug | T&M | Closed | 0 | 1 | Green | No | 2025-03-19 | 2024-03-18 | 2026-03-19
55 | Veolia WTS Services USA-Fixed Price-POD-008558 | 81000 | Core | Non-Strikezone | India | MS | Fixed Fee | Closed | In Progress |  | Green | No | 2025-10-25 | 2024-12-04 | 2025-12-03
17 | Intuit Inc-Time and Materials-Cust Success-Prepaid-PR-005042 | 78100 | Core | Core RPA | India/US | Staff Aug | T&M | Closed | 0 | 2 | Green | No | 2025-07-17 |  | 2024-11-16
34 | Take-Two Interactive Soft-Hybrid-Prepaid-008816 | 78100 | Core | Core RPA | India | Staff Aug | T&M | Closed | Green | No | Green | No | 2025-04-29 | 2024-04-30 | 2026-04-29
54 | Take-Two Interactive Soft-Time and Materials-Prepaid-009051 | 78100 | Core | Non-Strikezone | India | Staff Aug | T&M | Closed | In Progress |  | Green | No | 2025-09-27 | 2024-07-24 | 2026-07-23
21 | The Dow Chemical Company-Service Credit Prepaid-008497 | 76950 | Core | Core RPA | India | Delivery | Fixed Fee | Closed |  |  | Green | No | 2025-02-20 |  | 2026-07-29
3 | Hub International-Time and Materials-POD-009283 | 76800 | Growth | Comms Mining | India | Staff Aug | T&M | Closed | 3 | 1 | Green | No | 2025-07-17 |  | 2026-04-17
| MemorialCare Health Syste-Fixed Price-Prepaid-PR-006221 | 76000 | core | Non-Strikezone | India | MS | Fixed Fee | Closed | 0.25 | 1.5 | Green | No | 2025-12-31 | 2025-07-01 | 2025-12-31
1 | Hub International-Service Credit Prepaid-100% Discounted-PR-007973 | 75000 | Growth | Gen AI/DU/IDP | India | Staff Aug | Service Credit | Closed | 0.5 |  | Green | No | 2025-07-17 |  | 2025-09-05
45 | MGM Resorts International-T&M-Prepaid-100% discounted -010468 | 71470 | Core | Strikezone | India/US | Delivery | T&M | Closed | In Progress |  | Green | No | 2025-12-01 | 2025-08-14 | 2027-08-13
11 | Workday Inc-Fixed Price-POD-008494 | 65780 | Growth | Gen AI/DU/IDP | India/US | Delivery | Fixed Fee | Closed | 0 | 2 | Green | No | 2025-01-31 |  | 2025-01-23
40 | Workday Inc.-Fixed Price-Prepaid 100% Discounted-009613 | 65780 | Growth | Gen AI/DU/IDP | India/US | Delivery | Fixed Fee | Closed | Green | No | Green | No | 2025-07-31 | 2025-01-23 | 2026-03-22
57 | Tenet Business Services C-Fixed Price-Prepaid-010122 | 63660 | Core | Non-Strikezone | India | MS | Fixed Fee | Closed | In Progress |  | Green | No | 2025-09-06 | 2025-05-20 | 2025-12-31
35 | Bank of America (Global)-Time and Materials-Prepaid-009525 | 52800 | Core | Core RPA | India | Staff Aug | T&M | Closed |  |  | Green | No | 2025-06-30 | 2024-12-06 | 2025-06-30
59 | The Standard-Time and Materials-Prepaid 100% Discounted-010322 | 51000 | Core | Strikezone | India/US | Delivery | T&M | Closed | Closed | 51000 | Green | No |  | 2025-07-14 | 2026-07-13
26 | Continental Resources-Fixed Price-Service Credit Prepaid 100% discounted-007899 | 50000 | Growth | Gen AI/DU/IDP | India | Delivery | Service Credit | Closed | Green | No | Green | No | 2024-04-28 |  | 2026-10-29
29 | Tenet Business Services C-100% dicounted-Fixed Price-Prepaid-008032 | 50000 | Growth | Gen AI/DU/IDP | India | MS | Service Credit | Closed | 0 | 3.25 | Green | No | 2025-07-17 | 2023-09-20 | 2025-09-25
7 | PACCAR Inc-Time and Materials-Prepaid-006270 | 48521 | Growth | Gen AI/DU/IDP | India | Delivery | T&M | Closed | 0.25 | 0 | Green | No | 2025-07-17 |  | 2025-06-26
25 | Wabtec Corporation-Hybrid-Prepaid-100% Discounted-009666 | 46040 | Core | Core RPA | India/US | Delivery | T&M | On Hold |  |  | Green | No | 2025-10-17 | 2025-02-11 | 2025-05-19
39 | Wabtec Corporation-Hybrid-Prepaid-100% Discounted-009666 | 46040 | Core | Core RPA | India/US | Delivery | T&M | Closed |  |  | Green | No | 2025-07-31 | 2025-02-11 | 2025-07-31
51 | Wabtec Corporation-Fixed Price-POD Project ID PR-009839 | 46040 | Core RPA | Non-Strikezone | India/US | Delivery | Fixed Fee | Closed |  | Green | Green | No | 2025-10-17 | 2025-02-11 | 2027-02-10
12 | WEX Inc-Hybrid-Prepaid-008995 | 44795 | Growth | Gen AI/DU/IDP | India/US | Staff Aug | T&M | Closed | 0.5 | 0.25 | Green | No | 2025-03-31 |  | 2025-07-15
5 | Lydonia Te-America Fujiku-Time and Materials-POD-008092 | 43725 | Growth | Gen AI/DU/IDP | India | Staff Aug | T&M | Closed | 0 | 0.25 | Green | No | 2025-01-21 |  | 2025-10-09
56 | Lydonia Te-USI Service Co-Time and Materials-POD-008284 | 41184 | Growth | Non-Strikezone | India | Staff Aug | T&M | Closed | In Progress |  | Green | No | 2025-05-24 | 2023-12-01 | 2025-11-30
13 | Weitzman Management Corp-Fixed Price-POD-009016 | 28600 | Growth | Gen AI/DU/IDP | India/US | Delivery | Fixed Fee | Closed | 1 | 0 | Green | No | 2025-01-31 |  | 2026-07-21
22 | E. & J. Gallo-Fixed Price-Prepaid-009309 | 26263 | Growth | Gen AI/DU/IDP | India/US | Delivery | Fixed Fee | Closed |  |  | Green | No | 2025-05-16 |  | 2024-11-11
20 | The Dow Chemical Company-Fixed Price-Prepaid-008658 | 25000 | Core | Core RPA | India/US | Delivery | Service Credit | Closed | 1.5 | 1 | Green | No | 2025-07-17 |  | 2026-09-09
46 | Zscaler Inc-Hybrid-Service Credit-Prepaid-100% Discounted-009841 | 25000 | Core | Non-Strikezone | India | Staff Aug | Service Credit | Closed |  |  | Green | No | 2025-09-11 | 2025-02-24 | 2026-02-24
4 | Hub International-Time and Materials-POD-PR-008841 | 19200 | Growth | Comms Mining | India | Staff Aug | T&M | Closed | 0.5 | 0 | Green | No | 2025-07-17 |  | 2025-11-27
42 | DENSO International Ameri-Time and Materials-Prepaid-006333 | 15000 | Growth | Gen AI/DU/IDP | India | MS | T&M | Closed | 0.5 | 0 | Green | No | 2025-07-13 | 2023-07-12 | 2025-07-13
14 | Motiva Enterprises LLC-Fixed Price-Partial Prepaid-009024 | 14355 | Growth | Gen AI/DU/IDP | India/US | Staff Aug | Fixed Fee | Closed | 0 | 1 | Green | No | 2025-07-17 |  | 2026-07-24
44 | Nissan North America-Time and Materials-Prepaid-PR-007895 | 12000 | Core | Core RPA | India | Staff Aug | T&M | Closed |  |  | Green | No | 2025-08-07 | 2023-08-09 | 2025-08-07
30 | Qatar International Islam-Fixed Price-Prepaid-009237 | 4264 | Growth | Test Automation | India | Delivery | Fixed Fee | Closed |  |  | Green | No | 2025-01-18 | 2024-02-10 | 2025-01-30
19 | FMC Corporation-Time and Materials-POD-010491 | 4200 | Platform Migration | Strikezone | India | Staff Aug | T&M | Closed | In Progress | 4200 | Green | No | 2025-10-01 | 2025-08-22 | 2027-08-21
50 | PSSD-1067 - Internal Cross Charge - Micron Automation Hub Migration |  | Growth | Non-Strikezone | India/US | Delivery | T&M | Closed |  |  | Green | No | 2025-12-01 | 2025-08-01 | 2026-07-31
38 | Lydonia Te-Angelo Gordon-Time and Materials-POD-009816 |  | Core RPA | Non-Strikezone | India | Staff Aug | T&M | Closed |  |  | Green | No | 2025-12-01 | 2025-02-13 | 2027-02-12
25 | Hub International-Time and Materials-POD-PR-009743 |  | Growth | Strikezone | India | Delivery | T&M | Closed | Closed |  | Green | No |  | 2025-01-31 | 2027-01-30
33 | Hub International-Time and Materials-Postpaid-PR-010758 | 128750 | Growth | XP/GenAI/Comms Mining | India | Delivery | T&M | Closed | In Progress |  | Green | No | 2026-02-01 | 2025-10-27 | 2027-10-26 | Hitesh Kumar | India
36 | Hub International-Hybrid-POD-010346 | 121127 | Growth | XP/GenAI/Comms Mining | india | Delivery | T&M | Closed | In Progress | 6.5 | Green | No | 2026-02-01 | 2025-07-22 | 2027-07-21 | Hitesh Kumar | India
Note on B44: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Sagar, Shikha, Sukannya, Sunil Closed in Jan 2025
Note on B46: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Priya Kannan Closed in Jan 2025
Note on C49: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Zero $ SOW- extension of PR-008494
Note on B66: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Priya Kannan Closed in Jan 2025